Job Number @ Type here

Functional Specification Template

C7523 / C7524 – Design – Public Utility Plant (PUP) Addendum

Replaces Section 2.10 Public Utility Plant (PUP) (Item No. PD 11)' of the 'C7523 – Preliminary Design Functional Specification Template.' and Section '2.6 Public Utility Plant (PUP) (Item No. DD 07)' of 'C7524 – Detailed Design Functional Specification Template'

- To be used as a guide when compiling project-specific specifications.

- @ = project-specific detail required.

- For clauses / items not required – insert text “Not Required” in clause heading, do not delete clause.

- Delete this table when document finalised.

July 2025

Contents

1	Public Utility Plant – Detailed Design	1

1.1	Definition of terms	1

1.2	Referenced documents	1

1.3	Quality system requirements	2

1.3.1	Hold Points, Witness Points and Milestones	2

1.4	Existing documentation	3

1.5	Design deliverables	3

1.6	General requirements for NTUI	3

1.6.1	Local requirements	3

1.6.2	Site validation plan	4

1.6.3	Permits and approvals	4

2	Design Analysis	4

2.1	NTUI Vibration Assessment and exclusion zones	4

2.1.1	Land Requirements outside of project boundary	5

2.2	NTUI Design models – BIM	6

2.3	Project specific requirements	6

2.4	NTUI report – Preliminary and detailed design	6

2.4.1	Letter to authorities	6

2.5	Report for Contract Administration	7

2.6	Payment	7

Attachment 1 – Design Checklist	8

Attachment 2 – Suitability of Early Works for NTUI Checklist	13

Attachment 3 – Design Workflow	15

Attachment 4 – Notification of Initial Design and Commitment to Betterment Approach	19

Attachment 5 – PUP Notification of Roadworks / Network Conflicts Letter Templates	22

# Public Utility Plant – Detailed Design

[Delete this text - This document has been drafted to provide as much detail as possible. The requirements and checklists should be customised to fit the scope and type of project work that is required.]

## Definition of terms

The terms used in this Functional Specification shall be as defined in Clause 1.1 of C523 Preliminary Design.

The Consultant / Contractor is advised that while there are a number of definitions used in the department, for the purposes of this Functional Specification, Non-Transport Utility Infrastructure (NTUI) relates to all infrastructure not owned by the department that is in the State Controlled Road Corridor (SCRC). Non-Transport Utility is a general term for a service and infrastructure owner / provider, (electricity, gas, telecommunications, water, wastewater and so on.), incorporating public and private networks.

Public Utility Plant (PUP) is deemed to cover only non-transport utility infrastructure permitted under another act with conditions, specifically municipal water and sewerage, fixed and radio telecommunications (but not mobile towers), distribution and transmission gas and electricity (including third party owned streetlighting) under State and Federal legislation.

All other third party utilities, commercial or otherwise, and irrespective of their similarities to PUP, that are located in the project Works area including; railways, tramways, aqueduct, conduit, water channel, pipeline (water, bulk water, etc.), fixed mechanical conveyor, tower pole, cable (electrical, fibre optic, copper or otherwise), electrical installations or any other utility plant that may be affected by the project is not included in this Functional Specification. Where however, these assets are not nominated in Section 1.6.1 for liaison, design and mitigation purposes, but are preset within the scope of works area, the consultant shall list / nominate them on the drawings and advise the Transport and Main Roads Project Manager in order for the department to confirm the scope for these AWE assets in the design.

Where these third party assets are nominated in Section 1.5.3 (example SEQ Water) they are to be managed similar to PUP in regards to conflict identification, asset owner liaison and mitigation strategies, however will generally come under a separate commercial arrangement to be managed by TMR and the asset owner.

## Referenced documents

Referenced documents in this Functional Specification are listed in Table 1.2.

Table 1.2 – Referenced documents

| Reference | Title |
| --- | --- |
| BS 5228-2:2009 | Code of Practice for Noise and Vibration Control on Construction and Open Sites, Part 2: Vibration |
| DIN 4150-3:1999 | Vibration in Buildings – Part 3: Effects on Structures |
| MRTS50 | Specific Quality System Requirements |
| MRTS56 | Construction Surveying |
| NTUMDM | Non-Transport Utility Management and Design Manual |
| - | TMR Surveying Standards, Part 1 and Part 2 |

Where standards differ, the Transport and Main Roads' standards and other technical publications take precedence.

## Quality system requirements

### Hold Points, Witness Points and Milestones

General requirements for Hold Points, Witness Points and Milestones are detailed in Clause 8.3 of MRTS50 Specific Quality System Requirements. They are defined in the following ways:

- Hold Point means an identified point in a process beyond which the Contractor shall not proceed without written authorisation from the Administrator authorising release of the Hold Point.

- Witness Point means an identified point in a process where the Contractor is required to give the Administrator prior notice with the option to observe an activity.

- Milestone means a point in time within a project which marks the start or completion of an activity.

The Hold Points, Witness Points and Milestones applicable to this Functional Specification are summarised in Table 1.3.1.

Hold Points, Witness Points and Milestones are to be customised to suit the size and scope of the project and in line with the Workflow and Checklist.

Table 1.3.1 – Hold Points, Witness Points and Milestones

Project Manager: delete / add relevant Hold Points, Witness Points and Milestones as applicable.

| Clause | Hold Point | Witness Point | Milestone |
| --- | --- | --- | --- |
| 1.5 | @ Type here Drafted a NTUI report documenting all the decisions, agreements and findings on NTUI. (Preliminary Design Package) |  |  |
| 1.6.2 | @ Type here Submit Site Validation |  |  |
| 2.1 | @ Type here Submit Design Predicted Construction Vibration Assessment report |  | @ Type here Engaged subcontractors to undertake survey and potholing Works in accordance with AS 5488 (if it was not already undertaken in the Business Case as Early Works) |
| 2.5.1 | Received letter(s) of endorsement for the IFC drawings for contestable works |  |  |

## Existing documentation

Project Manager: insert details about existing information available to the Consultant if / where applicable.

## Design deliverables

- The Consultant shall complete the Detailed Design deliverables in two stages being the:

  - Initial (Preliminary) Design Hold Point, and

  - the final Detailed Design package.

The requirements and deliverables for each phase is included within Non-Transport Utility Management and Design Manual (NTUMDM) and this Functional Specification. Deliverables for Design and Construct projects shall be in accordance with the contract for the project.

## General requirements for NTUI

Alterations to existing NTUI must comply (where possible) to department document NTUMDM. Any deviation from these requirements must be documented.

The Consultant shall ensure that administrative data, and any early Site investigations, of existing NTUI conform to specified quality level documented in Transport and Main Roads standards and specifications.

The Consultant is required to utilise the Transport and Main Road's workflow process and checklist developed as a framework to assist with considering NTUI in the Design Phase. The Consultant is required to adapt these documents to fit the circumstances of the individual project and provide a short rationale to justify any adaptation. Copies of the workflow and checklist templates are included as Attachments 1, 2 and 3 of this Functional Specification.

### Local requirements

Project Manager: include reference to local requirements including the planning section of the district that has a GIS database of written undertakings from service providers. This includes offers to relocate services at no expense to the department. The Consultant shall contact relevant district officers and determine if any written undertakings have been made that may affect the project.

The Consultant shall ensure that all Authorities that control the following services will be consulted:

- @ Type here Electricity

@ Type here Sewage

@ Type here Gas

@ Type here Water

@ Type here Telecommunications carriers

@ Type here Local Government

@ Type here Streetlighting, and

@ Type here Department’s ITS&E

### Site validation plan

If a Site Validation Plan was undertaken in the Business Case stage and is less than twelve months old, a review and validation that the data is still current should be undertaken by the Consultant with the utilities and BYDA.

Otherwise, the Consultant shall prepare a Site Validation Plan with matrix identifying where potholing and/or cable location Works should be undertaken. The Site Validation Plan shall be submitted to the Project Manager for approval. Hold Point

Upon the release of the Site Validation Plan Milestone, the Consultant shall engage a service locator to undertake the Site validation Works. Unless otherwise agreed the consultant shall be responsible for the Principal Contractor duties when engaging the services of a subcontractor.

The Consultant shall liaise with the Project Manager to arrange for surveyors to record the survey data of validation Works. Survey data shall be recorded as per the MRTS56 Construction Surveying requirements so that the Project Manager can upload it into the relevant Transport and Main Roads project, GIS and Building Information Management (BIM) systems.

### Permits and approvals

The Consultant is responsible for obtaining all relevant permits and approvals from service authorities, the department (Transport and Main Roads), the Department of Environment and Science (DES) and so on when undertaking Site validation Works, i.e. gas spotter required when potholing gas main.

Confirm all relocations are contained within the identified project boundary of the Approved Recommended Option, unless otherwise agreed with third party.

# Design Analysis

## NTUI Vibration Assessment and exclusion zones

The Consultant shall undertake a Design Predicted Construction Vibration Assessment specific to the type of utility asset. The Consultant shall meet the requirements specified in applicable industry standards, asset owner's requirements, British Standard BS 5228-2:2009 and or German Standard DIN 4150-3:1999 as nominated by the Consultants' vibration specialist. The design predicted construction vibration assessment from preliminary design shall be updated as required during the detailed design.

The assessment shall be conducted and/or supervised by a Registered Professional Engineer of Queensland (RPEQ) with relevant experience in vibration assessment for infrastructure projects. The report shall be submitted to the Department by the signing RPEQ and not the report author unless they are the signing RPEQ, prior to submission to the relevant service authority for discussion. Hold Point

The Consultant's RPEQ (conducting the vibration assessment) shall consult with the design team to obtain expected details of construction. The Consultant will assess a range of different equipment sizes and methods (e.g. different piling methods, multiple roller sizes, multiple hammer sizes, milling / profiling machinery, combined plant for insitu subgrade treatments etc.) to determine if there are any restrictions/limitations to equipment selection in order to maintain safe working distances and /or allowable vibration limits. Whilst vibration issues should be resolved in Preliminary Design, where a vibration issue arises, it is expected that the Consultant's RPEQ (conducting the vibration assessment) shall develop a solution to vibration issues in consultation with the NTUI design team and revise the vibration assessment to resolve any issues (e.g. plant for triple blend mix of the subgrade cannot be reduced in size therefore adjustment to the NTUI treatment strategy (protect/relocate and so on) is required.

It is the responsibility of the Consultant to provide the assessing RPEQ (conducting the vibration assessment) with contact details and relevant information of the asset owner's vibration criteria and other requirements. Where further information is required, where the asset owner may not have a criterion, the asset owners preferred process (if utilising BS 5228-2:2009 or GIN 4150-3:1999 is not accepted without conditions) shall be requested by the Consultant's RPEQ (conducting the vibration assessment) in writing and all correspondence to and from the asset owner shall be appended to the NTUI Report and Design Predicted Construction Vibration Assessment report.

The Consultant shall provide the assessing RPEQ (conducting the vibration assessment) information on the type, location, condition, etc. of assets. Where this information is not provided, the Consultant's RPEQ (conducting the vibration assessment) is to source this information from the asset owners. The information obtained by the Consultant's RPEQ (conducting the vibration assessment) shall be clearly documented in the assessment report.

The Consultant's RPEQ (conducting the vibration assessment) in the preparation of the Design Predicted Construction Vibration Assessment Report, shall summarise vibration issues, equipment restrictions, etc and provide project specific vibration mitigation. Vibration mitigation shall be provided to ensure that safe working distances and/or vibration limits are maintained.

### Land Requirements outside of project boundary

Where relocation Works involve construction on private property, the Consultant shall advise the responsible authorities that it is their responsibility to obtain any necessary permits from the property owner (for example, clearing work, excavation, and so on).

Notwithstanding the above, NTUI relocation shall:

- conform with the following local requirements

- @ Type here

Project Manager: include reference to local documents for example Underground Services

## NTUI Design models – BIM

Where the main contract does not require a BIM model, the Consultant shall prepare a 3D model (12D or IFC) of all utilities and underground services for the purpose of clash detection and coordination. The model shall include all existing and proposed utilities and underground services including electrical and ITS, power poles, light poles and traffic poles (as applicable), SW drainage network, culverts, surface levels and subgrade levels. All other items specified in the parent Functional Specification C7523 and C7524 shall apply.

Spaced proofed service corridors with vertical / horizontal asset alignments are to be delivered to the utility provider as part of non-contestable works. Due to long lead times in design and procurement of communications, electrical and gas utilities, this information will allow utility providers to begin develop a cost estimate / quotes for the design phases.

## Project specific requirements

The Consultant is advised of the following project specific requirements which must be considered:

- Electricity and Streetlight relocations

@ Type here Project Manager to add any project specific requirements – undergrounding of overhead cables, clearances, agreements to relocate facilities, and so on.

- Water and Sewerage main relocations

@ Type here Project Manager to add any project specific requirements - clearances to maintenance / control equipment, and so on.

- Low-impact and non-low impact (e.g. mobile towers) Telecommunications

@ Type here Project Manager to add any project specific requirements – clearances to new pits, agreements to relocate facilities, and so on.

- Distribution and Transmission Gas pipelines, and

@ Type here Project Manager to add any project specific requirements – clearances to maintenance / control equipment, and so on.

## NTUI report – Preliminary and detailed design

The Consultant is required to include a report on NTUI within the Project Planning Report (NTUI Preliminary Design Package).

The Consultant is required to include a report on NTUI within the Design Development Report (NTUI Detailed Design Package). The report shall include all of the deliverables as required in the NTUMDM and this Functional Specification.

### Letter to authorities

If not already completed, the consultant shall draft letters to allow the Principal to formally inform each PUP owner that the project may have a conflict with their assets. Letter Templates have been made available in Attachment 5 for use in these circumstances.

After detailed design drawings and documentation are finalised, a no objection letter / email correspondence is required from the utility providers in order to progress to construction. Hold Point

## Report for Contract Administration

The Consultant shall prepare a report on the status of NTUI treatment or relocation Works to assist the Contract Administrator. This report shall include indicative timeframes provided from the service authority for the proposed relocation / protection Works, confirmation of alignment acceptance from the service authority and road authority, details of access requirement and timeframes for easement approval (if applicable), a copy of the relevant service authority plans, a copy of the relevant service authority specifications (if any), an estimate for the proposed Works plus the Principal's letter(s) to the relevant authority(s).

## Payment

All costs associated with the preparation of the preliminary plans, documents and reports shall be provided for under Fixed Fee Item PD 11.

All costs associated with the preparation of detailed design plans, specifications, contract documentation and reports shall be provided for under Fixed Fee Item DD 07. This includes all work necessary to arrange for the relevant Utility Authority to prepare non-contestable works quotes for the protection or relocation of services.

The Consultant shall not be required to pay for the cost of the preparation of the plans and specifications by the relevant non-contestable authority. The Consultant shall arrange for these costs to be invoiced directly to the Principal.

All costs associated with the preparation of the NTUI clash detection and coordination model shall be allowed for in Item No. PD25 / DD27 Building Information Modelling (BIM). Where main contract does not require a project wide BIM model, then this item shall be itemised specifically as PD25 / DD27 Building Information Modelling (BIM)-NTUI only.

# Attachment 1 – Design Checklist

| Program Delivery and Operations | Issued Date: xx/xx/20 |
| --- | --- |
| Design Stage Checklist Completed by: Project Name: Project / Contract No: | Version: 1.0 Date: xx/xx/20 |

Note: This checklist has been developed to provide general guidance for NTUI management on Road Infrastructure Projects. It can be used by departmental staff and Consultants to check that key aspects of utility management are covered in this stage. For any proposed changes or amendments to the checklist, please send all correspondence to tmr.techdocs@tmr.qld.gov.au.

| Item | Tasks / Description | Date Completed | Comments |
| --- | --- | --- | --- |
| 1.0 |  |  |  |
| 1.7.1.1 | Consulted with the Department's ITS&E and Corridor Management teams for their input to the Preliminary Design stage. |  |  |
| 1.7.1.2 | Coordinated meetings with NTU providers to share Early Design information, scope, requirements, timeframe, standards (particularly in relation to vibration exposure), review previous upgrade and/or betterment agreements. |  |  |
| 1.7.1.3 | Requested condition survey or asset validation from NTU providers, if this was not completed in the Business Case stage (or is more than 12 months old). |  |  |
| 1.7.1.4 | Confirm and obtain agreement from the NTU providers and departmental Project Manager on any design review process, for assets where the department or its Contractor will undertake relocation designs. |  |  |
| 1.7.1.5 | Reviewed Site validation / pothole plans and engaged subcontractors to undertake survey and potholing Works in accordance with TMR Surveying Standards (if it was not already undertaken in the Business Case as Early Works). Data from any potholing must be carefully checked and validated and additional potholing may be required to fill any information gaps. |  |  |
| 1.7.1.6 | Undertook survey validation reviews of the data provided. |  |  |
| 1.7.1.7 | Cross-referenced the survey data into the NTUI model and updated the utility services to reflect the change in quality level and the indicative information (QL-D) is removed / trimmed. |  |  |
| 1.7.1.8 | Confirmed all NTUI features / layers in the model have been turned on. E.g. Stay wire, pits, valves, hydrants, manholes etc. |  |  |
| 1.7.1.9 | Developed preliminary alignments of proposed NTUI relocations and confirmed if standard alignments are achievable. |  |  |
| 1.7.1.10 | Assessed and confirmed the line and level of existing NTUI to the extent necessary to enable potential conflicts (including any height clearances to wires) to be identified and discussed in detail with the responsible authorities. |  |  |
| 1.7.1.11 | Provided updated NTUI drawings with alignments to NTU providers for review and agreement. The updated drawings should include the conflicts register at the back, stating which NTUI are not impacted, for protection and for relocation. |  |  |
| 1.7.1.12 | Engaged NTU providers or design consultants to undertake preliminary and detailed design of NTUI relocations. |  |  |
| 1.7.1.13 | Confirmed and obtained formal engagement offers and any initial upfront payments. |  |  |
| 1.7.1.14 | Reviewed the terms of engagement, timeframe, costs, deliverables etc and signed off by Transport and Main Roads. |  |  |
| 1.7.1.15 | Once the preliminary NTUI relocation designs are developed, they must be cross referenced with all the designs into the NTUI model and undertook a 'space proofing' review (to ensure the design fits in all networks) undertaken. |  |  |
| 1.7.1.16 | Checked all new NTUI designs were not in conflict with existing or new infrastructure. |  |  |
| 1.7.1.17 | Met with NTU providers and agreed on all protection and relocation Works. |  |  |
| 1.7.1.18 | Assessed and confirmed any impacts to the environments, cultural heritage, future maintenance and access for utilities etc. |  |  |
| 1.7.1.19 | Developed the NTUI BIM model for existing and proposed NTUI, inclusive of mains, conduits, pits, manholes etc. |  |  |
| 1.7.1.20 | Assessed and confirmed all new NTUI for constructability and risk. |  |  |
| 1.7.1.21 | Assessed and confirmed NTUI construction staging and temporary Works, if applicable. |  |  |
| 1.7.1.22 | Discussed and agreed with NTU providers if Transport and Main Roads can undertake any civil Works on behalf of the NTU providers. E.g. Excavation, laying conduits and backfill. |  |  |
| 1.7.1.23 | Requested and received updated NTUI estimates and bill of quantities. |  |  |
| 1.7.1.24 | Assessed NTUI for Early Works and planned for Early works where practical. Refer to the Early Works Suitability Checklist for details. |  |  |
| 1.7.1.25 | Drafted a NTUI report documenting all the draft design plans, decisions, agreements and findings on NTUI. |  |  |
| 1.7.1.26 | Consulted with the Department's ITS&E and Corridor Management teams for their input to the Detailed Design stage. |  |  |
| 1.7.1.27 | Coordinated meetings with NTU providers to share Detailed Design information, scope, requirements, timeframe etc. |  |  |
| 1.7.1.28 | Assessed and confirmed if any additional survey and potholing Works are required, especially at tie-in locations to existing NTUI. |  |  |
| 1.7.1.28 | Assessed and confirmed proposed NTUI designs complies with the NTUMDM. |  |  |
| 1.7.1.30 | Assessed and confirmed proposed NTUI trenchless designs complies with the following Transport and Main Road's technical specifications. - MRTS140 Horizontal Directional Drilling - MRTS141 Microtunneling and Pipe Jacking - MRTS142 Thrust Boring and Auger Boring |  |  |
| 1.7.1.31 | Cross referenced all final NTUI designs into the NTUI model and undertook a final ‘space proofing’ review. This is normally assessed in 12d or similar software packages. |  |  |
| 1.7.1.32 | Assessed and confirmed proposed NTUI designs meets future maintenance and safe access to utilities. E.g. Manhole covers, valve covers, pit lids are raised or lowered to suit finished surface levels. Driveway / easement access to utilities are not blocked or adversely impacted. |  |  |
| 1.7.1.33 | Assessed and confirmed minimum clearance to aboveground powerlines / cables are achieved with the new finished surface levels including exclusion zones for maintenance staff. |  |  |
| 1.7.1.34 | Assessed and confirmed if any power pole relocations can be relocated outside of the area of interest, subject to Site specific risk assessment (e.g. roadside hazard). If not, are safety barriers warranted? |  |  |
| 1.7.1.35 | Assessed and confirmed clearances to cut batter slopes, subgrade excavation level, invert of table drains etc. |  |  |
| 1.7.1.36 | Assessed and confirmed clearances to existing and new structures, as well as new guardrail, fence line etc. E.g. Bridge piers, gantry footings, traffic light/CCTV footings. |  |  |
| 1.7.1.37 | Assessed and confirmed if any property connections are impacted and if so, specified the mitigation measures. |  |  |
| 1.7.1.38 | Assessed and confirmed which existing NTUI assets are required to be grout filled and capped and/or removed with justifications for grout filling and plans clearly showing treatments. |  |  |
| 1.7.1.39 | Finalised the certified (RPEQ) and endorsed NTUI relocation design drawings and obtained confirmation through the departmental Project Manager that all alignments are accepted by the utilities and department. |  |  |
| 1.7.1.40 | Finalised the NTUI BIM model, if applicable. The minimum Level of Development LOD required is 300 UNO in project brief or contract. |  |  |
| 1.7.1.41 | Finalised constructability and risk reviews for electrical NTUI. |  |  |
| 1.7.1.42 | Finalised constructability and risk reviews for water / sewer NTUI. |  |  |
| 1.7.1.43 | Finalised constructability and risk reviews for telecommunication NTUI. |  |  |
| 1.7.1.44 | Finalised constructability and risk reviews for gas NTUI. |  |  |
| 1.7.1.45 | Finalised NTUI estimate in 3PCM and bill of quantities (either as a Principal’s cost or itemised MRS). |  |  |
| 1.7.1.46 | Finalised contractual arrangements with NTU providers including utilities' payment of NTUI upgrades / betterment, and identification of their management strategy regarding disruption of essential services (such as medical, emergency services, police, defence forces). |  |  |
| 1.7.1.47 | Finalised NTUI Supplementary Specifications. Ensure NTU providers contact details, construction specifications, timeframe and any other information the Contractor needs to know are included. |  |  |
| 1.7.1.48 | Finalised Early Works package and early procurement, if applicable. |  |  |
| 1.7.1.49 | Finalised the Detailed Design NTUI Report. |  |  |

# Attachment 2 – Suitability of Early Works for NTUI Checklist

| Suitability of Early Works for NTUI Checklist | Issued Date: xx/xx/xx |
| --- | --- |
| To be used in planning, design and construction stages. Completed by: Project Name: Project / Contract No: | Version: 1.0 Date: xx/xx/xx |

The purpose of Early Works is to reduce risk in the delivery / time constraint in the main construction contract and avoid project delays and latent conditions, which ultimately results in variation claims to Transport and Main Roads. However, Early Works should be assessed on a case-by-case scenario and do not work for all situations.

| Suitable for Early Works | Tick if applicable to your project | Not Suitable for Early Works | Tick if applicable to your project |
| --- | --- | --- | --- |
| NTUI which require a long lead time to procure and install (e.g. 33 kV electrical cables, transmission gas mains, mobile towers, large diameter, water / sewer mains), Large Optical and copper cables |  | NTUI relocations into an embankment area which currently does not exist (e.g. the road finished surface level is getting raised considerably) |  |
| Relocation of overhead NTUI infrastructure below ground or like-for-like into a new area |  | When extensive bulk earthworks are required to be completed first |  |
| NTUI relocations near railways, airfields or ports, where any delays will be detriment to the project budget |  | Highly trafficked urban areas where multiple open road excavation will negatively impact traffic conditions and/or pedestrian movements |  |
| Multiple unknown NTUI which were not identified in BYDA / GIS and only found during potholing investigations and none of the NTU providers are aware of the asset |  | Minor Works Contract (e.g. new acceleration lane, minor road safety upgrade projects etc) where the construction value is less than $5M and risk is low |  |
| NTUI relocations that can be installed in shared trenches or trenchless excavation (e.g. HDD or pipe jacking) |  | NTUI relocations onto a new bridge or onto an existing bridge where it will impact any upgrade Works to the bridge |  |
| NTUI relocations which can only occur in certain periods or non-peak periods of the year |  |  |  |
| NTUI relocations into an easement which requires land resumption |  |  |  |
| NTUI relocations out of the existing roadway or road widening areas and into the new border zone area |  |  |  |
| High risk or complex PUP relocations which may cause delays to the main construction program (e.g. multiple connections / shutdowns) |  |  |  |
| NTUI relocations which are high risk to safety and may cause delays (e.g. relocation Works on bridges) |  |  |  |

# Attachment 3 – Design Workflow

# Attachment 4 – Notification of Initial Design and Commitment to Betterment Approach

| Date: |  |  |  |
| --- | --- | --- | --- |
| TMR Project No: |  | TMR Project Name: |  |
| Description of TMR Project (high level): |  |  |  |
| PUP Authority Contact: | Phone: |  | Email: |
| TMR Project Manager: | Phone: |  | Email: |

Checklist of utilities types and the parts of the Acts that empower Transport and Main Roads to require utilities undertake protection and/or relocation Works on their network assets.

| Public Utility Type | Legislative Act to undertake protection / relocation Works by public utilities made under | Check the appropriate box |
| --- | --- | --- |
| Electricity | s.106 Electricity Act 1994 | ☐ |
| Distribution Gas | s.94 Gas Supply Act 2003 | ☐ |
| Transmission Gas | s.428 Petroleum and Gas (Production and Safety) Act 2004 | ☐ |
| Water Distribution (QUU / Unitywater) | s.53BX South East Queensland Water (Distribution and Retail Restructuring) Act 2009 Part 3 - Public Entity Work | ☐ |
| Local Government Water | Transport Infrastructure Act 1994, Clause 82 | ☐ |
| Telecommunications | Transport Infrastructure Act 1994, Clause 82 | ☐ |
|  | Please note that some utilities have bespoke agency specific notification forms which must be used. Consultant should ask the Project Administrator for copies so that the agency specific form is used for these Utility Providers. |  |

[Letter template for Initial design and betterment approach commitment with Utility assets. This cannot be used instead of other notification]

[Insert Date]

Our ref		
Your ref		
Enquiries

[Utility entity]

[Insert Address]

Dear [Add Name of Addressee]

Notice of commencement of initial design which may affect [Insert Utility Name]'s network

In accordance with section [[Delete those that do not apply] s.106 Electricity Act 1994, s.94 Gas Supply Act 2003, s.428 Petroleum and Gas (Production and Safety) 2004, s.53BX South East Queensland Water (Distribution and Retail Restructuring) Act 2009, s.82 Transport Infrastructure Act 1994] I hereby give you notice of the following proposed roadwork preliminary design:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

To be carried out at the following location:

[Insert the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the utility Provider to identify all of its infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in the initial Design stage. While Transport and Main Roads intention is to avoid conflicts with existing Utility assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of our intentions in accordance with the appropriate legislative Act identified above.

Attached to this letter is an initial design outlining the section of the State Controlled Road we are planning to upgrade for your information and records.

In addition to the proposed roadworks Transport and Main Roads would like to extend an offer [Insert Utility Name] to discuss opportunities for you save money and upgrade your network within the limits of this project if you are prepared to fund the upgrades and they do not delay our project. If you would like to take up this offer please contact Transport and Main Roads by [Insert Date]. Opportunities to upgrade your network during this project will be difficult to accommodate once we have progressed to 30% preliminary design so we encourage you to respond in writing to this offer after careful consideration confirming your intention.

Alternatively, [Insert Utility Name] may, within [Insert Days] Business Days of the date of receipt of this notice, make written submissions to Transport and Main Roads detailing your proposed upgrades and funding commitments. This timeframe may be extended upon consultation with Transport and Main Roads.

If you do not respond or contact us within the stated period from the date of receipt of this notice this offer will be retracted and we will continue to liaise with you to resolve those conflicts which are unavoidable.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

[Insert Name of Officer]
[Insert Title of Officer]

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

# Attachment 5 – PUP Notification of Roadworks / Network Conflicts Letter Templates

For Consultant to complete:

| Date: |  |  |  |
| --- | --- | --- | --- |
| TMR Project No: |  | TMR Project Name: |  |
| Description of TMR Project (high level): |  |  |  |
| PUP Authority Contact: | Phone: |  | Email: |
| TMR Project Manager: | Phone: |  | Email: |

Checklist of utilities and the parts of the acts that require you to notify them of w that may affect their assets:

| Public Utility Type | Legislative Act to undertake protection and/or relocation Works by Public Utilities made under | Check the appropriate box |
| --- | --- | --- |
| Electricity | Electricity Act 1994, Clause 99 | ☐ |
| Distribution Gas | Gas Supply Act 2003, Clause 91 | ☐ |
| Transmission Gas | Petroleum and Gas (Production and Safety) Act 2004, Clause 427 | ☐ |
| Water Distribution (QUU / Unitywater) | South East Queensland Water (Distribution and Retail Restructuring) Act 2009 Part 3 - Public Entity Work, Clause 53BU | ☐ |
| Local Government Water | Transport Infrastructure Act 1994, Clause 80 | ☐ |
| Telecommunications | Transport Infrastructure Act 1994, Clause 80 | ☐ |
|  | Please note that some utilities have bespoke agency specific notification forms which must be used. Consultant should ask the Project Administrator or Departmental Delegate for copies so that the agency specific form is used for these Utility Providers. |  |

[Letter template for Notice of Conflict with Utility assets - Electricity]

[Insert Date]

Our ref		
Your ref		
Enquiries

[insert Entity]

[Insert Address]

Dear [Add Name of Addressee]

Notice of work affecting electricity entity’s Works under section 99 of the Electricity Act 1994

In accordance with section 99 of the Electricity Act 1994, I hereby give you notice of the following proposed roadworks:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

to be carried out at the following location:

[Insert the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the electricity entity to identify all of its electricity infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in the Detailed Design stage. While Transport and Main Roads have attempted to avoid conflicts with existing PUP assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of the identified conflicts in accordance with the appropriate legislative Act identified above.

Attached to this letter are the documents identified in the below table. These documents provide details of the Transport and Main Roads project, PUP conflicts identified, and the interim treatment being proposed to address the identified PUP conflicts.

It is requested that you review the attached documents and advise on your, and other relevant representatives from your organisation, availability for a follow up meeting with Transport and Main Roads representatives on [Enter Date and Time] at [Enter Location for Meeting] to discuss the identified conflicts, confirm if any assets have been overlooked and the suitability of the proposed treatment options.

A copy of the following documents regarding the proposed roadworks is attached to this notice. [Remove any that do not apply and this instruction]

| Attachment Number | Description | Date / Version of document |
| --- | --- | --- |
| 1 | Road corridor drawings (identifying existing PUP location) |  |
| 2 | Type Crossing Sections |  |
| 3 | Resumption drawings, showing new property boundaries |  |
| 4 | Longitudinal sections adjacent to new property boundaries |  |
| 5 | Longitudinal sections along new / existing pavement alignment |  |
| 6 | PUP Conflict identification table (Conflict Matrix) |  |
| 7 | Quality Level A and/or B Subsurface Utility Information |  |
| 8 | Proposed treatments (high level protection / relocation) |  |
| 9 | Summary of relevant Geotechnical Investigation Reports |  |
| 10 | Summary of relevant Environmental, Cultural Heritage and Native Title reports |  |
| 11 | Proposed milestone program for Transport and Main Roads Works (include details of resumption process, fencing relocations, PUP relocations / protection commencement, PUP relocations / protection completion (if PUP relocation/protection delivered as Early Works), road construction commencement, road construction completion) |  |
| 12 | Details of design consultant engaged for Transport and Main Roads project |  |
| 13 | Additional information: [Enter Description] |  |

Alternatively, [Insert Utility Name] may, within 14 calendar days of the date of receipt of this notice, make written submissions to Transport and Main Roads about the proposed roadworks. This timeframe may be extended upon consultation with Transport and Main Roads.

Information about the vibration exposure standards for your assets, and any other technical relevant standards or guidelines that may apply to working near your assets would be appreciated.

Before finalising the proposed roadworks, Transport and Main Roads will consider any written submissions made by you within the stated period.

If you do not respond within the stated period from the date of receipt of this notice, Transport and Main Roads may proceed to finalise the proposed roadworks.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

[Insert Name of Officer]
[Insert Title of Officer]

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

[Letter template for Notice of Conflict with Utility assets – Distribution Gas]

[Insert Date]

Our ref		
Your ref		
Enquiries

[insert Distribution Gas Organisation's name]

[Insert Address]

Dear [Add Name of Addressee]

Notice of road works on a State-controlled road under section 91 of the Gas Supply Act 2003

In accordance with sections 90 – 91 of the Gas Supply Act 2003, I hereby give you notice of the following proposed roadworks:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

to be carried out at the following location:

[Insert a description of the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the gas distributor to identify all of its gas infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in the Detailed Design stage. While Transport and Main Roads have attempted to avoid conflicts with existing PUP assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of the identified conflicts in accordance with the appropriate legislative Act identified above.

Attached to this letter are the documents identified in the below table. These documents provide details of the Transport and Main Roads project, PUP conflicts identified, and the interim treatment being proposed to address the identified PUP conflicts.

It is requested that you review the attached documents and advise on your, and other relevant representatives from your organisation, availability for a follow up meeting with Transport and Main Roads representatives on [Enter Date and Time] at [Enter Location for Meeting] to discuss the identified conflicts, confirm if any assets have been overlooked and the suitability of the proposed treatment options.

A copy of the following documents regarding the proposed roadworks is attached to this notice. [Remove any that do not apply and this instruction]

| Attachment Number | Description | Date / Version of document |
| --- | --- | --- |
| 1 | Road corridor drawings (identifying existing PUP location) |  |
| 2 | Type Crossing Sections |  |
| 3 | Resumption drawings, showing new property boundaries |  |
| 4 | Longitudinal sections adjacent to new property boundaries |  |
| 5 | Longitudinal sections along new / existing pavement alignment |  |
| 6 | PUP Conflict identification table (Conflict Matrix) |  |
| 7 | Quality Level A and/or B Subsurface Utility Information |  |
| 8 | Proposed treatments (high level protection/ relocation) |  |
| 9 | Summary of relevant Geotechnical Investigation Reports |  |
| 10 | Summary of relevant Environmental, Cultural Heritage and Native Title reports |  |
| 11 | Proposed milestone program for Transport and Main Roads Works (include details of resumption process, fencing relocations, PUP relocations / protection commencement, PUP relocations / protection completion (if PUP relocation/protection delivered as Early Works), road construction commencement, road construction completion) |  |
| 12 | Details of design consultant engaged for Transport and Main Roads project |  |
| 13 | Additional information: [Enter Description] |  |

Alternatively, [Insert Utility Name] may, within 30 business days of the date of receipt of this notice, make written submissions to Transport and Main Roads about the proposed roadworks. This timeframe can be extended upon consultation with Transport and Main Roads.

Information about the vibration exposure standards for your assets, and any other technical relevant standards or guidelines that may apply to working near your assets would be appreciated.

Before finalising the proposed roadworks, Transport and Main Roads will consider any written submissions made by you within the stated period.

If you do not respond within 30 business days from the date of receipt of this notice, Transport and Main Roads may proceed to finalise the proposed roadworks.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

[Insert Name of Officer]
[Insert Title of Officer]

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

[Letter template for Notice of Conflict with Utility assets – Transmission Gas]

NOTE! There may be a contract regulating this crossing, check with Commercial Property before sending this letter]

[Insert Date]

Our ref		
Your ref		
Enquiries

[insert Transmission Gas Organisation's name]

[Insert Address]

Dear [Add Name of Addressee]

Notice of road works on a State-controlled road under section 427 of the Petroleum and Gas (Production and Safety) Act (2004)

In accordance with section 427 of the Petroleum and Gas (Production and Safety) Act 2004, I hereby give you notice of the following proposed roadworks:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

to be carried out at the following location:

[Insert a description of the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the gas distributor to identify all of its gas infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in the Detailed Design stage. While Transport and Main Roads have attempted to avoid conflicts with existing PUP assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of the identified conflicts in accordance with the appropriate legislative Act identified above.

Attached to this letter are the documents identified in the below table. These documents provide details of the Transport and Main Roads project, PUP conflicts identified, and the interim treatment being proposed to address the identified PUP conflicts.

It is requested that you review the attached documents and advise on your, and other relevant representatives from your organisation, availability for a follow up meeting with Transport and Main Roads representatives on [Enter Date and Time] at [Enter Location for Meeting] to discuss the identified conflicts, confirm if any assets have been overlooked and the suitability of the proposed treatment options.

A copy of the following documents regarding the proposed roadworks is attached to this notice. [Remove any that do not apply and this instruction]

| Attachment Number | Description | Date / Version of document |
| --- | --- | --- |
| 1 | Road corridor drawings (identifying existing PUP location) |  |
| 2 | Type Crossing Sections |  |
| 3 | Resumption drawings, showing new property boundaries |  |
| 4 | Longitudinal sections adjacent to new property boundaries |  |
| 5 | Longitudinal sections along new / existing pavement alignment |  |
| 6 | PUP Conflict identification table (Conflict Matrix) |  |
| 7 | Quality Level A and/or B Subsurface Utility Information |  |
| 8 | Proposed treatments (high level protection / relocation) |  |
| 9 | Summary of relevant Geotechnical Investigation Reports |  |
| 10 | Summary of relevant Environmental, Cultural Heritage and Native Title reports |  |
| 11 | Proposed milestone program for Transport and Main Roads Works (include details of resumption process, fencing relocations, PUP relocations / protection commencement, PUP relocations / protection completion (if PUP relocation/protection delivered as Early Works), road construction commencement, road construction completion) |  |
| 12 | Details of design consultant engaged for Transport and Main Roads project |  |
| 13 | Additional information: [Enter Description] |  |

Alternatively, [Insert Utility Name] may, within 30 business days of the date of receipt of this notice, make written submissions to Transport and Main Roads about the proposed roadworks. This timeframe can be extended upon consultation with Transport and Main Roads.

Information about the vibration exposure standards for your assets, and any other technical relevant standards or guidelines that may apply to working near your assets would be appreciated.

Before finalising the proposed roadworks, Transport and Main Roads will consider any written submissions made by you within the stated period.

If you do not respond within 30 business days from the date of receipt of this notice, Transport and Main Roads may proceed to finalise the proposed roadworks.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

[Insert Name of Officer]
[Insert Title of Officer]

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

[Letter template for Notice of Conflict with Utility assets – Local Government Water]

[Insert Date]

Our ref		
Your ref		
Enquiries

[insert LG Water Utility name]

[Insert Address]

Dear [Add Name of Addressee]

Notice of road works on a State-controlled road under section 80(2) of the Transport Infrastructure Act 1994

In accordance with section 80 of the Transport Infrastructure Act 1994 ("the TIA"), I hereby give you notice of the following proposed roadworks:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

to be carried out at the following location:

[Insert the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the water authority to identify all of its water infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in the Detailed Design stage. While Transport and Main Roads have attempted to avoid conflicts with existing PUP assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of the identified conflicts in accordance with the appropriate legislative Act identified above.

Attached to this letter are the documents identified in the below table. These documents provide details of the Transport and Main Roads project, PUP conflicts identified, and the interim treatment being proposed to address the identified PUP conflicts.

It is requested that you review the attached documents and advise on your, and other relevant representatives from your organisation, availability for a follow up meeting with Transport and Main Roads representatives on [Enter Date and Time] at [Enter Location for Meeting] to discuss the identified conflicts, confirm if any assets have been overlooked and the suitability of the proposed treatment options.

A copy of the following documents regarding the proposed roadworks is attached to this notice. [Remove any that do not apply and this instruction]

| Attachment Number | Description | Date / Version of document |
| --- | --- | --- |
| 1 | Road corridor drawings (identifying existing PUP location) |  |
| 2 | Type Crossing Sections |  |
| 3 | Resumption drawings, showing new property boundaries |  |
| 4 | Longitudinal sections adjacent to new property boundaries |  |
| 5 | Longitudinal sections along new / existing pavement alignment |  |
| 6 | PUP Conflict identification table (Conflict Matrix) |  |
| 7 | Quality level A and/or B Subsurface Utility Information |  |
| 8 | Proposed treatments (high level protection / relocation) |  |
| 9 | Summary of relevant Geotechnical Investigation Reports |  |
| 10 | Summary of relevant environmental, cultural heritage and native title reports |  |
| 11 | Proposed milestone program for Transport and Main Roads Works (include details of resumption process, fencing relocations, PUP relocations / protection commencement, PUP relocations / protection completion (if PUP relocation/protection delivered as Early Works), road construction commencement, road construction completion) |  |
| 12 | Details of design consultant engaged for Transport and Main Roads project |  |
| 13 | Additional information: [Enter Description] |  |

Alternatively, [Insert Utility Name] may, within 20 business days of the date of receipt of this notice, make written submissions to Transport and Main Roads about the proposed roadworks. Before finalising the proposed roadworks, Transport and Main Roads will, consider any written submissions made by you within the stated period.

Information about the vibration exposure standards for your assets, and any other technical relevant standards or guidelines that may apply to working near your assets would be appreciated.

Transport and Main Roads notes you [are/are not] part of the October 2017 'TMR/Local Government Cost Sharing Arrangement' and all processes in the arrangement regarding your water/sewerage assets [apply/do not apply].

If you do not respond within 30 business days from the date of receipt of this notice, Transport and Main Roads may proceed to finalise the proposed roadworks.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

[Insert Name of Officer]
[Insert Title of Officer]

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

[Letter template for Notice of Conflict with Utility assets – QUU/Unitywater]

[Insert Date]

Our ref		
Your ref		
Enquiries

[insert QUU/Unitywater]

[Insert Address]

Dear [Add Name of Addressee]

Notice of Public Entity Work under section 53BU of the South-East Queensland Water (Distribution and Retail Restructuring) Act 2009

In accordance with section 53BU of the South-East Queensland Water (Distribution and Retail Restructuring) Act 2009 ("the SEQ Water Act"), I hereby give you notice of the following proposed roadworks:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

to be carried out at the following location:

[Insert the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the distributor-retailer to identify all of its water infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in Detailed Design stage. While Transport and Main Roads have attempted to avoid conflicts with existing PUP assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of the identified conflicts in accordance with the appropriate legislative Act identified above.

Attached to this letter are the documents identified in the below table. These documents provide details of the Transport and Main Roads project, PUP conflicts identified, and the interim treatment being proposed to address the identified PUP conflicts.

It is requested that you review the attached documents and advise on your, and other relevant representatives from your organisation, availability for a follow up meeting with Transport and Main Roads representatives on [Enter Date and Time] at [Enter Location for Meeting] to discuss the identified conflicts, confirm if any assets have been overlooked and the suitability of the proposed treatment options.

A copy of the following documents regarding the proposed roadworks is attached to this notice. [Remove any that do not apply and this instruction]

| Attachment Number | Description | Date / Version of document |
| --- | --- | --- |
| 1 | Road corridor drawings (identifying existing PUP location) |  |
| 2 | Type Crossing Sections |  |
| 3 | Resumption drawings, showing new property boundaries |  |
| 4 | Longitudinal sections adjacent to new property boundaries |  |
| 5 | Longitudinal sections along new / existing pavement alignment |  |
| 6 | PUP Conflict identification table (Conflict Matrix) |  |
| 7 | Quality Level A and/or B Subsurface Utility Information |  |
| 8 | Proposed treatments (high level protection / relocation) |  |
| 9 | Summary of relevant Geotechnical Investigation Reports |  |
| 10 | Summary of relevant Environmental, Cultural Heritage and Native Title reports |  |
| 11 | Proposed milestone program for Transport and Main Roads Works (include details of resumption process, fencing relocations, PUP relocations / protection commencement, PUP relocations / protection completion (if PUP relocation/protection delivered as Early Works), road construction commencement, road construction completion) |  |
| 12 | Details of design consultant engaged for Transport and Main Roads project |  |
| 13 | Additional information: [Enter Description] |  |

Alternatively, [Insert Utility Name] may, within 30 business days of the date of receipt of this notice, make written submissions to Transport and Main Roads about the proposed roadworks.

Information about the vibration exposure standards for your assets, and any other technical relevant standards or guidelines that may apply to working near your assets would be appreciated.

Before finalising the proposed roadworks, Transport and Main Roads will, within the terms of section 53BU(3) of the SEQ Water Act, consider any written submissions made by you within the stated period.

If you do not respond within 30 business days from the date of receipt of this notice, Transport and Main Roads will proceed to finalise the proposed roadworks.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

[Insert Name of Officer]
[Insert Title of Officer]

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

[Letter template for Notice of Conflict with Utility assets – Telecommunications]

[Insert Date]

Our ref		
Your ref		
Enquiries

[insert Telco name]

[Insert Address]

Dear [Add Name of Addressee]

Notice of road works on a State-controlled road under section 80(2) of the Transport Infrastructure Act 1994

In accordance with section 80 of the Transport Infrastructure Act 1994 ("the TIA"), I hereby give you notice of the following proposed roadworks:

| Department of Transport and Main Roads Project No: | Project Name: |  |
| --- | --- | --- |
| Description of TMR Project (high level): |  |  |
| PUP Authority Contact: | Phone: | Email: |
| TMR Project Manager: | Phone: | Email: |

to be carried out at the following location:

[Insert the location of the proposed roadworks, including the name of the state-controlled road and sufficient details to enable the Telco to identify all of its telecommunications infrastructure that may be impacted by the proposed roadworks]

The Transport and Main Roads project identified above is currently in the Detailed Design stage. While Transport and Main Roads have attempted to avoid conflicts with existing PUP assets as part of this design development, some conflicts may be unavoidable. This letter is advising you of the identified conflicts in accordance with the appropriate legislative Act identified above.

Attached to this letter are the documents identified in the below table. These documents provide details of the Transport and Main Roads project, PUP conflicts identified, and the interim treatment being proposed to address the identified PUP conflicts.

It is requested that you review the attached documents and advise on your, and other relevant representatives from your organisation, availability for a follow up meeting with Transport and Main Roads representatives on [Enter Date and Time] at [Enter Location for Meeting] to discuss the identified conflicts, confirm if any assets have been overlooked and the suitability of the proposed treatment options.

A copy of the following documents regarding the proposed roadworks is attached to this notice. [Remove any that do not apply and this instruction]

| Attachment Number | Description | Date / Version of document |
| --- | --- | --- |
| 1 | Road corridor drawings (identifying existing PUP location) |  |
| 2 | Type Crossing Sections |  |
| 3 | Resumption drawings, showing new property boundaries |  |
| 4 | Longitudinal sections adjacent to new property boundaries |  |
| 5 | Longitudinal sections along new / existing pavement alignment |  |
| 6 | PUP Conflict identification table (Conflict Matrix) |  |
| 7 | Quality Level A and/or B Subsurface Utility Information |  |
| 8 | Proposed treatments (high level protection / relocation) |  |
| 9 | Summary of relevant Geotechnical Investigation Reports |  |
| 10 | Summary of relevant Environmental, Cultural Heritage and Native Title reports |  |
| 11 | Proposed milestone program for Transport and Main Roads Works (include details of resumption process, fencing relocations, PUP relocations / protection commencement, PUP relocations / protection completion (if PUP relocation/protection delivered as Early Works), road construction commencement, road construction completion) |  |
| 12 | Details of design consultant engaged for Transport and Main Roads project |  |
| 13 | Additional information: [Enter Description] |  |

Alternatively, [Insert Utility Name] may, within 20 business days of the date of receipt of this notice, make written submissions to Transport and Main Roads about the proposed roadworks. This period may be extended upon TMR's discretion.

Information about the vibration exposure standards for your assets, and any other technical relevant standards or guidelines that may apply to working near your assets would be appreciated.

Before finalising the proposed roadworks, Transport and Main Roads will, consider any written submissions made by you within the stated period.

If you do not respond within 30 business days from the date of receipt of this notice, Transport and Main Roads will proceed to finalise the proposed roadworks.

An extract of sections 80-82 of the TIA is attached to this notice for your convenience.

Should you have any queries in relation to this notice, please do not hesitate to contact [Insert Details of Contact Officer].

Yours sincerely

[Insert Name of Officer]
[Insert Title of Officer]

Xxxxxxxx
xxxxxxx
address
address Queensland 4000

Telephone	+61 7 
Website	www.tmr.qld.gov.au
Email	xxxx@tmr.qld.gov.au
ABN 39 407 690 291

Extracts of sections 80 - 82 of the Transport Infrastructure Act 1994

80 Specification of chief executive’s requirements about public utility plant

(1) The construction, augmentation, alteration or maintenance of public utility plant on a State-controlled road must be undertaken in accordance with the chief executive’s requirements and at the expense of the owner of the plant.

(2) Road works on a State-controlled road made necessary by the construction, augmentation, alteration or maintenance of public utility plant on a State-controlled road must be undertaken in accordance with the chief executive’s requirements and at the expense of the owner of the plant.

(3) Requirements mentioned in subsection (1) or (2) are to be notified in writing to the owner of the plant within a reasonable period.

81 Information by owner of public utility plant to chief executive

(1) A person who wants to take action mentioned in section 80 must give a written notice to the chief executive of the person’s intention to carry out work on a State-controlled road within a reasonable time before taking the action.

(2) If public utility plant is constructed, augmented, altered or maintained on a State-controlled road, the owner of the plant must prepare records that adequately define the location of the plant on the road at the time of the construction, augmentation, alteration or maintenance of the plant.

(3) The owner of public utility plant on a State-controlled road must, if asked by the chief executive, supply information to the chief executive to define adequately the location of the plant in a specified area.

82 Liability for damage or expenses

(1) Unless the chief executive otherwise agrees, the chief executive is not liable for damage caused by the chief executive to public utility plant on a State-controlled road if—

(a) the chief executive had, before the damage was caused, asked for information under section 81(3) from the owner of the plant and—

(i) the owner had not, within a reasonable time, complied with the request; and

(ii) the damage was caused because of the failure to comply with the request; or

(b) information supplied to the chief executive under section 81(3) does not define in adequate detail the location of the plant and the damage was caused because of the failure to define in adequate detail the location of the plant; or

(c) the damage was caused because of the plant having been constructed, augmented, altered or maintained other than under the chief executive’s requirements under this division.

(2) If the chief executive incurs additional expense in carrying out road works on a State-controlled road because—

(a) the owner of public utility plant had not supplied within a reasonable time information asked for by the chief executive under section 81(3); or

(b) information supplied to the chief executive did not define in adequate detail the location of public utility plant; or

(c) public utility plant had not been constructed, augmented, altered or maintained under the chief executive’s requirements; the owner of the plant is liable to pay to the chief executive the additional expense.