Objective of the estimate review: to certify that the estimate development process follows Transport and Main Roads cost estimating policy and processes as described in the current Project Cost Estimating Manual (PCEM) and the cost estimate is fit for purpose.

Peer review – must be conducted by a qualified and experienced person as described in PCEM.

Concurrence review - must be conducted by a suitably qualified and experienced person independent of the project and approved by the regional director for all QTRIP projects over $25 million.

| Estimate Prepared by: |  |  | Estimate Reviewed by: |  |  | Date of Review: |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: |  |  | Project Number: |  |  |  |  |
| Project Stage: | ☐ Strategic | ☐ Business Case |  | ☐ Preliminary Design | ☐ Detail Design |  | ☐ Tender |

| A. Conforming to policies, strategies, and standards |  | Y/N | Comments |
| --- | --- | --- | --- |
| - Does the estimate match project intent, scope, phase, and the stage? PCEM Ed 9 refer Section 4 and Section 5 |  |  |  |
| - Does the estimate comply with Cost Estimating Policy? PCEM Ed 9 refer Section 2 |  |  |  |
| - Does the estimate comply with the department’s estimate practices? PCEM Ed 9 refer Section 2.5 |  |  |  |
| - Does the estimate conform with other related policies in the department? PCEM Ed 9 refer Section 2.6 |  |  |  |
| - Does the estimate comply with the requirements for different phases in various project types? PCEM Ed 9 refer Table 2.4 |  |  |  |
| - Does the estimate comply with requirements of the projects that are funded by the federal government? PCEM Ed 9 refer Section 2.6.5 |  |  |  |
| - Has the PCB submitted (if applicable for projects funded by the federal government) being checked? PCEM Ed 9 refer Section 2.5.5 |  |  |  |
| B. Completeness of documentation submitted for review |  | Y/N3 | Comments |
| - Has the appropriate estimating method been used for the project types and stages and approved by the Project Manager? PCEM Ed 9 refer Section 9.1 (unit rate, first principles, Types 1, 2 and 3) |  |  |  |
| - Does the estimate include costs of all project stages? PCEM Ed 9 refer Section 3 (Construction costs, principals costs (each project phase costs and risk and contingencies) |  |  |  |
| - Have the principal’s costs derived from first principles? PCEM Ed 9 refer Section 3.3 |  |  |  |
| - Has the estimate classified into CapEx / OpEx dissections as required for reporting? PCEM Ed 9 Table2.6.5.1 |  |  |  |
| - Do the principal’s costs include all the components? PCEM Ed 9 Section 3.3, Table 3.3 (project management, principal’s obligations, resumptions, PUP, principal supplied materials, service levies, environmental offset costs etc.) |  |  |  |
| - Has the estimate been submitted in out-turned dollars? PCEM Ed 9 refer Section 11.1.10 |  |  |  |
| - Have the costs presented in appropriate project estimate structure components? PCEM Ed 9 ref Figure 3.1(a) and Figure 3.1(b) (DJC, IJC, margins, principals costs, escalation, risk and contingencies) |  |  |  |
| - Have factors influencing estimating considered during the estimate development? PCEM Ed 9 refer Figure 5.1.5 (scope, constraints, constructability, construction program, traffic management issues, location issues, PUP and sustainability / climate change issues) |  |  |  |
| - Has the estimate benchmarked against district benchmarking data? PCEM Ed 9 refer Section 8 (global rates, key item rates, construction production rates) |  |  |  |
| - Does the submission for review include electronic copies of assumptions, construction program, submission schedule, risk register, probability distributions, simulation details and @Risk data files? PCEM Ed 9 refer Section 7.1 |  |  |  |
| C. Application of the recommended estimating tools |  | Y/N3 | Comments |
| - Does the cost items included in the submission schedule sufficiently cover for the scope and all phases of the project? PCEM Ed 9 refer Section 5.1 (scope, constraints, constructability, construction program, traffic management issues, location issues, PUP and sustainability / climate change issues) |  |  |  |
| - Have the estimating tools recommended by the department been used to develop the estimate, and have they presented in the appropriate format? PCEM Ed 9 refer Section 9.3 |  |  |  |
| D. Risk evaluation and contingency development |  | Y/N3 | Comments |
| - Is the risk assessment appropriate to produce the P90 estimate? PCEM Ed 9 refer Section 3.3.7 and 10.1 (risk register, benchmarking, strategic estimating matrix, @Risk) |  |  |  |
| - Is the risk assessment technique used for the risk analysis process appropriate? PCEM Ed 9 refer Section 10.1.19 and Section 10.1.20 (qualitative and quantitative approaches, Monte Carlo simulation) |  |  |  |
| - Have the project risks appropriately modelled Planned / Unplanned? PCEM Ed 9 refer Section 10.1.19 and Section 10.1.20 |  |  |  |
| - Has the risk register submitted in Risk Context Profile format? PCEM Ed 9 refer Section 10.1.19 and Section 10.1.20 |  |  |  |
| - Has the risk workshop been conducted to assess and verify risks as appropriate? PCEM Ed 9 refer Section 10.1.5 |  |  |  |
| - Has the project contingency allowance verified to ensure it lies within the recommended contingency range for this stage? PCEM Ed 9 refer Table 3.3.7 |  |  |  |
| - For Type 1 projects, have appropriate contingency allowances made against individual cost change categories? PCEM Ed 9 refer Section 3.3.7 and Section 10 |  |  |  |
| - Are the ranges applied to planned risks in the probabilistic model appropriate? PCEM Ed 9 refer Section 10.1.6.3 and Section 10.1.20 |  |  |  |
| - Are the consequence / likelihood ranges applied to unplanned risks reasonable? PCEM Ed 9 refer Section 10.1.6 |  |  |  |
| - Are the probability distribution (models) applied in @Risk are appropriate? PCEM Ed 9 refer Section 10.1.20 |  |  |  |
| ☐ Satisfactory (expected process controls are in place and used satisfactorily) ☐ Unsatisfactory (attach details of any controls that in your opinion are not in place and/or are not used satisfactorily) ☐ Approved ☐ Not approved |  |  |  |
| Signature: ___________________________________________ | Date: ____________________________________ |  |  |

To be completed by the Estimator.

To be reviewed by reviewer appointed by the Project Manager.

If yes, documentary evidence must be made available to the Region / District Director.