## Road Infrastructure Projects
Annexure E
RISK TABLE FOR DETERMINING CONTINGENCY FOR STRATEGIC ROAD PROJECTS
(Based on Australian Government Guidance Note 3B - Deterministic Contingency Version 2.0)
Complete cells with green shading
| Estimate Stage: | Strategic / Planning
Project Number:
Project Location:
Project Description:
Factor influencing the Estimate | Available information on which the Scoping Estimate is based | Highly Confident & Reliable | Reasonably Confident & Reliable | Not Confident & Not Reliable | Adopted Contingency
Project Scope | A set of well-defined project objectives and related performance criteria
| A design report (with all underlying assumptions and exclusions noted) | 6% | 7% | 9% | 7%
A set of concept drawings (covering all the physical scope and staging)
Identified significant risks (political, community, technical, financial)
Risks
| A detailed risk analysis | 6% | 7% | 9% | 9%
A project delivery method
Constructability | A constructability, staging and construction access review
|  | 3% | 4% | 5% | 4%
A construction timetable (with appropriate start up and handover periods)
Key Dates
| A set of project dates (to enable outturn cost to be assessed) Timing of the construction phase (for escalation assessment) | 1% | 2% | 3% | 2%
Site Specific Information
| Sufficient and documented investigation for concept design (geotechnical, heritage, environmental, technical, hydraulic) Enabling works (adequately identified & allowed in the estimate) | 5% | 6% | 9% | 9%
External interfaces (identified and defined in terms of scope, access and risk)
Project interfaces |  | 3% | 4% | 5% | 4%
Project assessment (extended or short site and greenfield / brownfield)
| Total contingency percentage to be adopted for an estimate with a 90% confidence level of not being exceeded: |  |  |  | 35%
| Total contingency percentage to be adopted for an estimate with a 50% confidence level of not being exceeded: (assessed to be 40% of the contingency percentage for a 90% confidence level of not being exceeded) |  |  |  | 14%

## Rail Infrastructure Projects
Annexure E
RISK TABLE FOR DETERMINING CONTINGENCY FOR STRATEGIC RAIL PROJECTS
(Based on Australian Government Guidance Note 3B - Deterministic Contingency Version 2.0)
Complete cells with green shading
| Estimate Stage: | Strategic / Planning
Project Number:
Project Location:
Project Description:
Factor influencing the Estimate | Available information on which the Scoping Estimate is based | Highly Confident & Reliable | Reasonably Confident & Reliable | Not Confident & Not Reliable | Adopted Contingency
Project Scope | A set of well-defined project objectives and related performance criteria
| A design report (with all underlying assumptions and exclusions noted) | 7% | 10% | 16% | 10%
A set of concept drawings (covering all the physical scope and staging)
Identified significant risks (political, community, technical, financial)
Risks
| A detailed risk analysis | 7% | 10% | 15% | 10%
A project delivery method
Constructability | A constructability, staging and construction access review
|  | 3% | 5% | 8% | 8%
A construction timetable (with appropriate start up and handover periods)
Key Dates
| A set of project dates (to enable outturn cost to be assessed) Timing of the construction phase (for escalation assessment) | 1% | 3% | 5% | 3%
Site Specific Information
| Sufficient and documented investigation for concept design (geotechnical, heritage, environmental, technical, hydraulic) Enabling works (adequately identified & allowed in the estimate) | 7% | 9% | 14% | 14%
External interfaces (identified and defined in terms of scope, access and risk)
Project interfaces |  | 5% | 8% | 12% | 8%
Project assessment (extended or short site and greenfield / brownfield)
| Total contingency percentage to be adopted for an estimate with a 90% confidence level of not being exceeded: |  |  |  | 53%
| Total contingency percentage to be adopted for an estimate with a 50% confidence level of not being exceeded: (assessed to be 60% of the contingency percentage for a 90% confidence level of not being exceeded) |  |  |  | 31.8%