## Road Infrastructure Projects
Annexure H: Escalation Calculator for Road Projects
This calculator is able to convert 'current' dollars using a proposed cash flow and user-defined escalation rates to an expenditure profile in estimated 'out-turn' dollars.
Project No.: | 12345678 |  |  | Enter data in green shaded cells
Financial Year | 2024-25 |  | Costs to date (sunk costs) | 2024-25 |  | 2025-26 |  | 2026-27 |  | 2027-28 |  | 2028-29
| Estimated Costs in 'current'* dollars ($,000) |  | Proposed Cash Flow in 'current'* dollars ($,000)
Estimated Cost Component / Project Phase | Base Estimate | Contingency Allowance | Actuals | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Check Totals
Concept | 150 | 30 |  | 0 | 0 | 150 | 30 | [6 empty] | 180
Development | 650 | 60 | [5 empty] | 420 | 45 | 230 | 15 |  |  | 710
Implementation | 2200 | 210 | [7 empty] | 1500 | 150 | 700 | 60 | 2410
Finalisation | 90 | 5 | [9 empty] | 90 | 5 | 95
Base Estimate | 3090 | 305 | 0 | 0 | 0 | 150 | 30 | 420 | 45 | 1730 | 165 | 790 | 65 | 3395
Total Project Cost | 3395 |  | 0 | 0 |  | 180 |  | 465 |  | 1895 |  | 855 |  | 3395
Converting Annual Cash Flow into 'out-turn' dollars
Adopted Escalation Rates % (p.a.) |  |  |  | 2.13% |  | 2.49% |  | 3.19% |  | 3.42% |  | 3.41%
Calculated Escalation Uplift Factor |  |  |  | 1 |  | 1.0249 |  | 1.0576 |  | 1.0938 |  | 1.1311
Escalation Amounts |  |  |  | 0 | 0 | 3.735 | 0.747 | 24.1896 | 2.5917 | 162.2118 | 15.4711 | 103.5385 | 8.519
Base Costs plus Contingency Amounts |  |  |  | 0 | 0 | 153.735 | 30.747 | 444.1896 | 47.5917 | 1892.2118 | 180.4711 | 893.5385 | 73.519
Annual Cash Flow Total |  |  |  | 0 |  | 184.482 |  | 491.7814 |  | 2072.6828 |  | 967.0575
[12 empty] | Total Escalation Amount: | 321.0037
[12 empty] | Outturned Project Costs: | 3716.0037

## Rail Infrastructure Projects
Annexure H: Escalation Calculator for Rail Projects
This calculator is able to convert 'current' dollars using a proposed cash flow and user-defined escalation rates to an expenditure profile in estimated 'out-turn' dollars.
Project No.: | 12345678 |  |  | Enter data in green shaded cells
Financial Year | 2024-25 |  | Costs to date (sunk costs) | 2024-25 |  | 2025-26 |  | 2026-27 |  | 2027-28 |  | 2028-29
| Estimated Costs in 'current'* dollars ($,000) |  | Proposed Cash Flow in 'current'* dollars ($,000)
Estimated Cost Component / Project Phase | Base Estimate | Contingency Allowance | Actuals | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Base Costs | Contingency | Check Totals
Concept | 150 | 30 |  | 0 | 0 | 150 | 30 | [6 empty] | 180
Development | 650 | 60 | [5 empty] | 420 | 45 | 230 | 15 |  |  | 710
Implementation | 2200 | 210 | [7 empty] | 1500 | 150 | 700 | 60 | 2410
Finalisation | 90 | 5 | [9 empty] | 90 | 5 | 95
Base Estimate | 3090 | 305 | 0 | 0 | 0 | 150 | 30 | 420 | 45 | 1730 | 165 | 790 | 65 | 3395
Total Project Cost | 3395 |  | 0 | 0 |  | 180 |  | 465 |  | 1895 |  | 855 |  | 3395
Converting Annual Cash Flow into 'out-turn' dollars
Adopted Escalation Rates % (p.a.) | [5 empty] | 2.76% |  | 2.69% |  | 2.78% |  | 3.2%
Calculated Escalation Uplift Factor |  |  |  | 1 |  | 1.0276 |  | 1.0552 |  | 1.0846 |  | 1.1193
Escalation Amounts |  |  |  | 0 | 0 | 4.14 | 0.828 | 23.2018 | 2.4859 | 146.3203 | 13.9554 | 94.2349 | 7.7535
Base Costs plus Contingency Amounts |  |  |  | 0 | 0 | 154.14 | 30.828 | 443.2018 | 47.4859 | 1876.3203 | 178.9554 | 884.2349 | 72.7535
Annual Cash Flow Total |  |  |  | 0 |  | 184.968 |  | 490.6877 |  | 2055.2757 |  | 956.9884
[12 empty] | Total Escalation Amount: | 292.9198
[12 empty] | Outturned Project Costs: | 3687.9198