## M4755 Page 1
Project Cost Estimate (Summary)
Project Details:
Project Number: | 404935
Project Name: | NCHD 250-127: Replacement of timber bridge over King John Creek, Beerburrum Road
Project Manager | John Smith
Project Location: | 127 - Beerburrum Road
Responsible Business Area | North Coast | Primary Work Location District |  | Maroochydore |  | LGA | Moreton Bay Regional
Project Phase | Business Case | Estimate Category (1 to 6) |  | 3 - Business Case |  | Contract Type | TIC - CO
Activity Group | Previous Years | Start Year | Start Year + 1 | Start Year + 2 | Subsequent Years | Total ($)
Principal's Costs
Concept Phase
Sunk Costs | [5 empty] | 0
Business Case estimate | [5 empty] | 0
0
[5 empty] | Concept Phase Sub Total | 0
Development Phase
Project management | [5 empty] | 0
Preliminary design | [5 empty] | 0
Detailed design | [5 empty] | 0
Resumptions | [5 empty] | 0
PUP relocations | [5 empty] | 0
0
[5 empty] | Development Phase Sub Total | 0
Implementation Phase
Project management | [5 empty] | 0
Contract administration | [5 empty] | 0
PAI and Qleave | [5 empty] | 0
Principal supplied materials | [5 empty] | 0
0
[5 empty] | Implementation Phase Sub Total | 0
Finalisation Phase
Project management | [5 empty] | 0
Finalisation Phase Costs | [5 empty] | 0
0
[5 empty] | Finalisation Phase Sub Total | 0
[5 empty] | Principal's Costs Total | 0
Construction Contractor's Costs
Traffic management | [5 empty] | 0
Earthworks | [5 empty] | 0
Drainage | [5 empty] | 0
Bridges | [5 empty] | 0
Pavement | [5 empty] | 0
Environmental works | [5 empty] | 0
0
[5 empty] | Construction Contractors Costs Total | 0
[5 empty] | Base Estimate (Principal's Cost + Construction Contractor's Cost) | 0
Risk and Contingency | [5 empty] | P50 | P90
Risk Cashflow (Planned Risk + Unplanned Risk) (P50) |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
Risk Cashflow (Planned Risk + Unplanned Risk) (P90) |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 0
[5 empty] | Total Project Cost in Current $ (Base Estimate + Contingency) | 0 | 0
[5 empty] | % of Contingency from the Base Estimate | #DIV/0! | #DIV/0!
Out-Turn Cost Calculation | [5 empty] | P50 | P90
| Previous Years | Start Year | Start Year + 1 | Start Year + 2 | Subsequent Years
Escalation Rate (%) | 0% | 2.13% | 2.49% | 3.19%
Escalation Factor | 1 | 1.0213 | 1.0467 | 1.0801
Cashflow (P50) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Cashflow (P90) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Escalation Amount (P50) | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0!
Escalation Amount (P90) | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0!
Out-Turn Cashflow (P50) | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0!
Out-Turn Cashflow (P90) | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0!
[5 empty] | Total Project Cost Out-Turn $ (Base Estimate + Contingency + Escalation) | #DIV/0! | #DIV/0!
# - For advice on Escalation refer QTRIP Development Guidelines and/or Project Cost Estimating Manual | [6 empty] | Page 1 of 2 M4755 June 2025

## M4755 Page 2
Project Cost Estimate continued ... page 2
Project Details:
Project Number: | 404935
Project Name: | NCHD 250-127: Replacement of timber bridge over King John Creek, Beerburrum Road
Project Manager | John Smith
Project Location: | 127 - Beerburrum Road
Responsible Business Area | North Coast | Primary Work Location District | Maroochydore | LGA | Moreton Bay Regional
Project Phase | Business Case | Estimate Category (1 to 6) | 3 Business Case | Contract Type | TIC - CO
Project Cost Estimate Certification
Project Cost Estimate | I certify that I have prepared this estimate in accordance with the Project Cost Estimating Manual based on the project information contained in the project scope statement, plans, documents and program of work included in this submission. I further certify that I have used appropriate risk management approach to develop contingencies and this is a P50/P90 risk adjusted estimate.
Estimator’s Name
| Signature |  |  | Date
Peer Review | I certify that I have conducted a peer review for this estimate in accordance with the requirements of the Project Cost estimating Manual. Points of difference between the estimator and the peer reviewer have been resolved and adjustments incorporated in the cost estimate as appropriate. Peer review undertaken on ______________.
Peer Reviewer's Name
| Signature |  |  | Date
Recommendation | I am satisfied that this P50/P90 estimate has been prepared in accordance with the Project Cost Estimating Manual and meets the requirements of approved project proposal, business case or project plan, as relevant. Any issues raised in the peer review have been resolved as per the Estimate Review Checklist. I recommend that this estimate be approved.
Project Manager's Name
| Signature |  |  | Date
Concurrence Project Review | I have undertaken the concurrence review for this project in accordance with the Project Cost estimating Manual and I am satisfied that the estimate is reasonable for this stage of the project. I also confirm that I am an independent third party and suitably qualified to undertake this review.
Reviewer's Name
| Signature |  |  | Date
Estimate Approval | I am satisfied that the project cost estimate was prepared for this project in accordance with the processes outlined in the current Project Cost Estimating Manual and that any issues raised in the concurrence review (if one was required) have been resolved as per the Estimate Review Checklist. Regional/District Director/ Program Manager/ Customer/ Sponsor – (Circle as appropriate)
Approver's Name
| Signature |  |  | Date
Page 2 of 2 M4755 June 2025