Appendix D - Checklist

Transport Infrastructure Project Delivery System

Volume 2 - Tendering for Infrastructure Works

March 2025

Appendix D – Checklist

| Vol 2 Ref | Action requirement | Action complete |  |
| --- | --- | --- | --- |
|  |  | Initials | Date |
| 5 | Tender Planning |  |  |
| 5.1 | Business Case decisions and details – - Identify all relevant decisions and supporting details - Establish adequate understanding Project Manager understands basis for project in Business Case |  |  |
| 5.2 | Responsibilities of Principal – - Consider project scope and circumstances - Identify project specific role and limits of responsibility for Tendering Manager - List responsibilities of Tendering Manager Responsibilities of Tendering Manager defined by Principal |  |  |
| 5.2.1 | Appoint Tendering Manager – - Consider project circumstances and project team. - Identify options available. Select and appoint. - Tendering Manager briefed on project and responsibilities Tendering Manager appointed and briefed by Principal |  |  |
| 5.3 | Appreciation of the project – - Assemble all relevant documents. - Obtain background briefings (as warranted). - Establish adequate understanding of the project and its circumstances. Tendering Manager fully prepared for Tender Planning |  |  |
| 5.4 5.3.2 5.3.1 5.3.4 5.4.3 5.5 | Planning steps by Tendering Manager – - Initiate preparation of TEP - Identify risks and opportunities - Identify appropriate tender selection method. - Determine tender selection criteria. - Probity Advisor warranted? - Prepare brief for TAP. Brief for TAP prepared |  |  |
| 6 | Tender development |  |  |
| 6.3.1 6.3.2 6.3.4 | Appoint TAP – - Panel membership requirements identified. - Candidate members identified, interviewed and availability confirmed. - Nominated Panel Members declare any conflict of interest. - Panel members appointed. - Australian Federal Government representation? - Panel members adequately briefed on the project. TAP appointed by Principal |  |  |
| 6.5 | Assemble / compose Tender Documents – - Design outputs complete? - Contract documents, including project specific details and definition of tender selection methodology prepared? - Supplementary conditions of tender prepared? - Scope finalised? - Tender Prototype peer reviewed by Designer and Project Manager? Prototype Tender Documents - complete and consistency checks carried out, reviewed by Designer, verified by Tendering Manager |  |  |
| 6.5.5 | Approval to call Tenders – - Tender documents complete? - Financial allocations available in the QTRIP? - Work site available – or adequate arrangements in place? - Utility alterations and service authority requirements defined and agreed? - TEP prepared? Principal's delegate approval to call tenders |  |  |
| 6.6.1 App E | Advertisement – Tender advertisement details approved by Tendering Manager |  |  |
| 6.6.1 | Issue Tender Documents – - Tenderer prequalified? - Obtain receipt for documents (Form C7501). Register of tender documents issued maintained |  |  |
| 6.6.2 | Deal with enquiries – - Nominated (experienced) officer appointed. - Record all responses (Form C7502). - Inform other tenderers (of enquiries and responses)? Register of enquiries and responses maintained |  |  |
| 6.6.3 | Notice to Tenderers – - Register and record of all Notices (Form C7503) - Obtain receipts from tenderers? Register of Notices and receipts maintained |  |  |
| 6.6.4 | Pre-tender meetings (including site inspections) – - Basis of meeting identified, and agenda planned. - Arrangements published (to all concerned). - Venue prepared, including displays. - Proceedings recorded minuted and minutes distributed. Pre-tender meetings planned and executed – verified by Tendering Manager |  |  |
| 7 | Tender analysis phase |  |  |
| 7.2 | Tender opening – - Opening date (and any extensions) confirmed. - Public opening or not? Nominated officers available for attendance? - Tender opening records established. - Record tender opening details (Form C7817). Tender opening procedures completed. |  |  |
| 7.3 7.3.3 7.3.3 7.3.4 7.3.5 7.3.6 7.3.7 7.3.8 | Tender Examination – - Check tender rates. - Check for compliance with Conditions of Tendering. - Deal with non-compliances (Table 7.1). - Resolve discrepancies (Table 7.2). (Form C7504). - Deal with tender conditions and assumptions (Tables 7.3 and 7.4). (Form C7504). - Deal with alternative tenders (Table 7.3.7): (Form C7505) - Identify if acceptable - Identify any intellectual property issues - Examine alternatives; Compare alternatives - Deal with unusually low bids. Tender examination complete – verified by Tendering Manager |  |  |
| 7.5.1 7.5.2 7.5.3 | Tender assessment – - Determine tenders in contention. (Form C7506 or C7507) - Undertake sensitivity analysis. (Form C7508) - Capability assessment: (examine "P" type schedules C7810_P1 to C7810_P8) - Financial capability - Technical capability - Clarify information Best tender identified by Selection Panel |  |  |
| 7.6 | Tender Assessment Report – - Documentation of assessment, conclusions and recommendation - Signatures of all Selection Panel Members and (if involved) Probity Advisor and/or Federal representative. - Report verified as complete Tendering Manager. - Copies of report to Project Manager, Probity Advisor, District Director, etc. - Record details of recommended tender. - Formal handover to Contract Administrator TAR and associated actions completed – verified by Project Manager |  |  |
| 8 | Financial Approval Procedures |  |  |
| 8.2 | Initial steps – - Tendering Manager (or nominee) enters project details into the FA Form (in 3PCM) - Dates for closing tenders and for expected completion of tender analysis updated (as warranted) Initial steps complete – verified by Project Manager |  |  |
| 8.2.1 8.2.2 8.2.3 | Authorisation – - Financial and Procurement Delegated Officer(s) for recommendation/approval identified – based on contract amount. - Tendering Manager enters details of recommended tender in 3PCM. - Complete the Contract Financial Approval Request form in Unifier. - Authorisation recorded. Authorisation to award contract complete – verified by Project Manager |  |  |
| 8.3 8.3.1 8.3.2 8.4 | Award of contract – - Tendering Manager forwards documents to Prequalification and Contracts Unit: - Tender Assessment Recommendation – refer Appendix J - Details of tenders received (Form 7817 – refer Standard Contract Provisions Roads Volume 1: Transport Infrastructure Contract Appendix A) - Register of Notice to Tenderers (Form C7503 – refer Appendix F) - District Tender Acceptance Report - Tender Correspondence, and - Original Winning Tender - Prequalification and Contracts Unit Contracts Officer verifies that all necessary documents are available and are complete. - Prequalification and Contracts Unit Contracts Officer prepares Letter of Acceptance - Letter of Acceptance signed by Delegated Officer (who has the necessary Statutory Delegation) and forwarded to successful contractor. - Instrument of Agreement prepared by the Principal and executed by both parties. - Advice to unsuccessful tenderers (letters and debriefings). Contract award action complete – verified by Project Manager |  |  |