# Bruce Highway Targeted Safety Program

to r

A llan Uhlm ann, Pro g ram D ire c

19 August 2025

# About the new program

A safer Br u c e Hi g h way

2

3

Building a safer Bruce

$9 billion for new safety works under the 80:20 joint funding arrangement

Accelerated delivery

Prioritising sections with high safety risk to combat crashes

Department of Transport and Main Roads

# Proposed work types

Wide centre line treatments, includes road widening and audio tactile line marking

Pavement strengthening

Overtaking lanes

Intersection upgrades

Widen narrow structures

Fatigue management and rest areas

Department of Transport and Main Roads	4

# Bruce Highway – location of work

North Queensland Region

Far North District

Northern District

TMR office

Central Queensland Region

Mackay-Whitsunday District

Fitzroy District

Southern Queensland Region

Wide Bay-Burnett District

5

Department of Transport and Main Roads

# Early Start Package

Construction

Commenced March 2025

Address sections with high safety risk

Engaging contractors through existing arrangements

Design

Commenced March 2025

Building towards development and delivery of overall pipeline of works

Direct engagement of designers by TMR

Department of Transport and Main Roads

# Construction – Strong progress

16 priority projects fast-tracked

to construction:

- 1 x complete

- 8 x under construction

- All remaining projects commencing this year

Above: Works are progressing to upgrade the Brooks Road intersection north of Gympie with a channelised right turn facility. Source: TMR image

7

Department of Transport and Main Roads

# Delivery – Next Steps

- Next round of construction following early start design – construction activities to commence in 2026.

- Priority pavement strengthening works – commencing in 25/26.

regional updates.

Further details to follow in

Above: Pavement strengthening undertaken near Hencamp Creek Road, Townsville as part of the Early Start Package.

Source: TMR image

8

Department of Transport and Main Roads

# Main Program – Update

Deficiencies confirmed and prioritised

PPR submitted to Australian Government on 29 July 2025

Additional interim projects identified

Panels established 2025

Contracts awarded through Panels 2026

9

Department of Transport and Main Roads

# Notional funding allocations by work type

| Work type | Notional allocation ($m) |
| --- | --- |
| Overtaking lanes | 860 |
| Intersection upgrades | 360 |
| Narrow bridges | 900 |
| Wide centre line treatments | 5,500 |
| Fatigue management and rest areas | 360 |
| Pavement strengthening | 620 |
| Program reserve | 400 |
| Total | 9,000 |

10

Department of Transport and Main Roads

# Notional funding allocations by District

| District | Notional allocation ($m) |
| --- | --- |
| Wide Bay Burnett | 700 |
| Fitzroy | 2,500 |
| Mackay Whitsunday | 2,100 |
| Northern | 1,300 |
| Far North | 1,600 |
| Statewide / Program Reserve | 700 |
| Total | 9,000 |

11

Department of Transport and Main Roads

Optional industry questionnaire

- 76 organisations responded

Key insights

- Agreement proposed approach will help accelerate procurement timelines and reduce tendering costs

- Readiness to contribute – capability and interest from across the market

- Industry wants more detail as it is available.

Interactive Industry Briefing

145 TMR staff and

365 industry representatives attended Diverse representation

63 questions raised and answered during 3 sessions

Very high levels of satisfaction with briefing: providing informative content – 90% opportunity to contribute feedback – 93%

Department of Transport and Main Roads	12

# Interactive Industry Briefing – Survey

Department of Transport and Main Roads	13

# Delivery Strategy Overview

- Broaden Access to Market – Tiered packaging and program approach (particularly for local and Tier 2 and 3 Constructors and local Designers).

- Expedite Procurement – Dedicated BHTSP Panels for Constructors, Designers and Contract Administrators. Will also help facilitate a strong rolling program of works.

- Panel Establishment Launching Soon – From August 2025. Procurement from Panels 2026 onwards.

14

# Key Areas of Focus

| Elements |  | Project packaging from prioritised deficiencies | Establish Panels (Constructor, Designer, CA) Contract Types | Capability Uplift | Develop demand profiles for key inputs | Program Standards | Re-use relevant existing processes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outputs |  | Flexibility in project sizing to limit overlap with competing major projects | Mix of Program D&C contracts and Construct- Only contracts | Joint industry training | Supply chain risk mitigations | Design note, Temp Traffic Management note, Rest Area design note, Real time traveller information | BHUP reporting and performance measures |
| Key Areas of Focus | Manage market constraints & inflationary pressures | Yes |  |  | Yes |  |  |
|  | Build industry capacity (upskilling, local suppliers, indigenous participation) | Yes | Yes | Yes | Yes | Yes | Yes |
|  | Mitigate impact on other BH projects | Yes |  |  | Yes |  |  |
|  | Procurement & delivery efficiency and productivity |  | Yes | Yes | Yes | Yes |  |
|  | Manage community and transport disruption |  |  |  |  | Yes |  |

Packaging

- Iterative process considering:

  - work type

  - priority

  - location

  - estimated value

  - work complexity

  - interfaces

  - pre-construction and planning already available

  - contract type (design, construct only, design and construct)

  - other projects or commitments

  - local TMR insights.

16

Packaging

Packaging

17

17

Panel Establishment

Panel Establishment

## Initial Panel establishment:

- Constructors

- Designers

- Contract Administrators

## Further Panels can be considered based on industry feedback and market risks and opportunities.

Department of Transport and Main Roads	18

# General Panel Establishment process

Proponents nominate:

- Location preference

- Prequalification status

- Project team

- Current commitments

Proponents agree to:

- Unamended Panel Conditions

- Unamended BHTSP specific contracts (including D&C designer subcontracts)

- Performance (KRA/KPI) requirements

- Specified commercial terms (including margin/fee caps for contractors)

19

Department of Transport and Main Roads

# Delivery approach

Decide to deliver as an individual project or as a program via the construction panel/s

Procure Initial Work Package (IWP)

Program contractor delivers IWP

Program contractor delivers AWP

TMR accepts offer as VFM

TMR evaluates performance against Key Result Areas (KRAs)

Procure and deliver individual project

Not performing

Offer does not represent Value For Money (VFM)

Performing

Program contractor develops offer for Additional Work Package (AWP) – multiple opps.

Department of Transport and Main Roads	20

Procurement of works under the Panel

  - Default position for procurement of all projects and programs is a two-stage RFP process

  - Under certain / exceptional circumstances an EOI process or a 3-2-1 dual procurement process may be undertaken.

Stage 1

Figure 1: Shortlist and competitive procurement process under the panel

Two- stage RFP

Process

Up to 3 Panel members invited to submit a Stage 1 proposal

Evaluate responses.

Shortlist up to 2 Panel member

Invite shortlisted tenderers to submit Stage 2 proposal

Evaluate tender responses including VfM assessment

Contract Award

Stage 2

Undertake approvals, negotiate and award contract to preferred tenderer

Procurement of works under the Panel

District Office invites Panel members based on the following key factors:

- Estimated contract value (i.e. </> $50m)

- Risk and complexity

- BHTSP performance

- Other factors

District Office undertakes a VfM Assessment including:

- Assessment of costs and quantities included in pricing proposal

- Verification by Independent Cost Estimator in reference to State developed estimate For instances where only 1 proposal is received, value for money will be tested against benchmarking and historical performance outcomes, or the project / program will be re- tendered

21 |

22 |

Contract Types

- Contractors must use BHTSP sub- contract for design works under TIC- TC

- Mandatory sub- contract agreement

- State side procurement (e.g. develop design for TIC-CO)

- TMR existing ‘Consultants for Engineering Projects’ (CFEP)

- Design & construction

- Standalone projects or program of projects

- Low to high risk / complexity

- New contract with adapted TIC-CO general terms

- Construction only (no design)

- Standalone projects (not program of projects)

- Low to medium risk

- TIC-CO base contract modified for BHTSP

Approach

- Contractor engaged to develop and finalise design and deliver the works

- State shares project cost risk and reward

Contract Types

BHTSP Construction Panel Agreement

BHTSP Design Panel Agreement

TIC-CO (Construct Only)

TIC-TC (Target Cost)

TMR (State Side) Consultant Contracts

Contractor (D&C Side) Design Consultants

Approach

- Design prepared by District Office

- Contractor engaged to deliver construction works

TIC-CO Key Terms

TIC-CO Key Terms

Proposed amendments to the TIC-CO commercial framework to enable greater transparency and comparability of pricing at tender and for variations.

Current TIC-CO commercial framework*

Schedule of Rates and / or Amounts

(All-in Amounts)

(Form M1 – Schedule of Rates or M2 – Schedule of Prices)

All-in rates inclusive of any overheads, profit and contingency

23 |

* Not including Lump Sum alternative

Proposed BHTSP TIC-CO commercial framework

(Use of form C7810.M10.TIC with updates)

Contingency

Offsite overheads and profit

Onsite overheads

Schedule of Rates - Direct Job Costs (DJCs) only

Bid back contingency pool

Capped % applied to DJCs and onsite overheads

Bid back % applied to DJCs

Unit pricing for labour, plant & equipment reflecting DJCs only exclusive of any overheads, profit or contingency

23

TIC-TC Key Terms

TIC-TC Key Terms

Potential Gainshare

Contractor’s Fee (Offsite overheads and profit)

Reimbursable Costs

Gain/pain share outcomes illustration

Target Cost

24 |

Department of Transport and Main Roads

Gainshare Amount

Where Actual Costs < Target Costs:

- Gainshare amount is shared 50:50 (Contractor and State)

- Contractor’s share is capped at 50% of Contractor’s Fee

Painshare Amount

Where Actual Costs > Target Costs:

- Painshare amount is shared 50:50 (Contractor and State)

- Contractor’s share is capped at 100% of Contractor’s Fee

24

# Program Notes – Technical Guidance

Design:

- Clarity of In and Out of scope elements

- Stipulates cross sectional widths, intersection standards and other safety treatments

- Guidance on pavement strengthening outcomes

Department of Transport and Main Roads

Temporary Traffic Management:

- Focus on

  - Road user experience

  - Worker and motorist safety

- Achieved by

  - Maintaining traffic flow

  - Selecting suitable speeds

25

Minimising travel time impacts

# Working with you

Co l l ab o r ati o n as Stan d ar d

26

Thank you and stay connected

www.tm r.q ld .g o v.au

TMRQld	@TMRQld	TMRQld	Department of Transport and Main Roads