Queensland Transport and Roads Investment Program (QTRIP) Industry Briefing 2025-26 to 2028-29

## Cent ra l Queensl a nd R eg i o n

Da v e G ro sse ,

R e g ion a l D ir e ct or

19 August 2025

# Central Queensland QTRIP and

Leadership

2

Mackay/Whitsunday QTRIP investment:

- $1.1b – 2025–26 to 2028–29

- $160m – 2025–26

Central West QTRIP investment:

- $396m – 2025–26 to 2028–29

- $98m – 2025–26

Fitzroy QTRIP investment:

- $2.1b – 2025–26 to 2028–29

- $442m – 2025–26

Department of Transport and Main Roads

Dave Grosse

Regional Director

Pat Aprile

District Director (Mackay/Whitsunday)

Gavin Hill District Director (Central West)

Kristy Hows

District Director (Fitzroy)

# Key QTRIP projects

Key QTRIP projects:

- Rockhampton Ring Road

- Proserpine - Shute Harbour Road

- Bruce Highway, Gladstone to Rockhampton, program of works

- Bruce Highway (Mackay - Proserpine), Goorganga, construct overtaking lanes

- Peak Downs Highway (Clermont – Nebo), construct overtaking lane

- Mackay - Bucasia Road and Golf Links Road intersection, upgrade intersection

- Bruce Highway (Mackay - Proserpine), O'Connell River to Proserpine (Goorganga Floodplain), upgrade flood immunity

Rockhampton Ring Road, construction of new Limestone Creek Bridge

3

Department of Transport and Main Roads

Bruce Highway Targeted Safety Program

Early start underway

- Construction:

  - 3 x projects delivering 2.2km Wide Centre Line Treatment (WCLT), Heavy Vehicle Rest Area and culvert upgrade progressing via sole invitee to deliver rapid upgrades to address safety deficiencies.

  - Open market tender recently closed to deliver 6.7km widening and install WCLT between Rockhampton – St Lawrence (Little Neerim Creek to Deep Creek).

- Design:

  - 7 x packages progressing with planning and design activities to facilitate next round of construction.

Next round of construction following early start design

- Rockhampton – St Lawrence: 4 x designs comprising approx. 29km of upgrades. Planning and design progressing. Designs to be completed progressively with tendering process (open market) for construction activities to commence in 2026.

- Mackay – Proserpine: 3 x designs comprising approx. 13.6km of upgrades, including intersection upgrade at Farleigh-Habana Road. Planning and design progressing. Design to be completed progressively with tendering process (open market) for construction activities to commence in 2026.

Priority pavement strengthening works

- Priority pavement strengthening works, commencing in 25/26*: Targeting priority sites between Gin Gin-Benaraby, Benaraby-Rockhampton, Rockhampton-St Lawrence, St Lawrence-Mackay, Mackay-Proserpine and Proserpine-Bowen.

  - Deliver approx. 36km pavement strengthening.

*Site development work in progress, subject to approvals.

5

Construction projects

| Project name | Indicative length (km) | Work type | Contract Type* | Procurement method | Prequal levels* | Indicative quarter to be called | Indicative contract value |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bruce Highway (Mackay - Proserpine), Goorganga, overtaking lanes, 2342944 | 1.8 | Construct overtaking lanes | TIC-CO | Open Market | R3, F20 | Oct-Dec 2025 | $10m - $25m |
| Bruce Highway (Benaraby - Rockhampton), 84.60 - 90.66km (Bajool), undertake safety upgrades; 3057688 | 4.2 | Shoulders, barriers and intersection | TIC-CO | Open Market | R3 | Jan-Mar 2026 | Up to $10m |
| Bruce Highway (Benaraby ‐ Rockhampton), Bajool, pavement reconstruction; 3591100 | 3.7 | Pavement Strengthening and WCLT | TIC-CO | Open Market | R3 | Jan-Mar 2026 | $10m - $25m |
| Proserpine - Shute Harbour Road packaged works, Paluma Road to Valley Drive, 1510612 and Valley Drive, 1197433 | 1.5 (in sections) | Capacity upgrade | TIC-CO | Open Market | R3, A3, F50 | Jan-Mar 2026 | $25m - $50m |
| Peak Downs Highway (Clermont - Nebo), Millennium Coal Mine to Carborough Downs Coal Mine, 1197099 | TBC | Construct overtaking lane | TIC-CO | Open Market | R3, F20 | Oct-Dec 2025 | Up to $10m |
| Fitzroy Developmental Road (Bauhinia - Duaringa), pave and seal; 3161934 | 4.8 | Pave and seal | TIC-CO | Open Market | R3 | Jul-Sep 2025 | Up to $10m |
| Dawson Developmental Road (Springsure - Tambo), priority upgrades; 2515815 | TBC | Floodway upgrades | TIC-CO | Open Market | R3, F20 | Jan-Mar 2026 | $10m - $25m |

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

6

Proserpine - Shute Harbour Road packaged works

| Project description | Paluma Road to Valley Drive, 1510612 - Capacity upgrades including widening, intersection improvements, provision of active transport facilities, enhanced route lighting and replacement/relocation of bus stop facilities. Valley Drive, 1197433 - Capacity upgrades including widening and reconfiguration of intersections along this section |
| --- | --- |
| Procurement method | Open Market |
| Prequal levels* | R3, A3, F50 |
| Approximate quarter to be called | Jan-Mar 2026 |

Proserpine - Shute Harbour Road

Paluma Road

intersection

intersection

Valley Drive

Proserpine - Shute Harbour Road packaged works indicative locality map

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

7

Design projects

| Project name | Indicative length (km) | Work type | Contract Type* | Procurement method | Prequal levels* | Approximate quarter to be called | Indicative contract value |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mackay - Bucasia Road and Golf Links Road intersection, upgrade intersection, 3543473 | 0.2 | Detailed Design | CFEP | Restricted Tender | HE3, ITS2, TE2 | Jul-Sep 2025 | Up to $10m |
| Bruce Highway (Mackay - Proserpine), O'Connell River to Proserpine (Goorganga Floodplain), upgrade flood immunity; 2342729 | 10.2 (in sections) | Detailed Design | CFEP | Open Market | HE3, BD3, HD3, GEC3, CE3 | Oct-Dec 2025 | $10m - $25m |
| Bruce Highway (Benaraby ‐ Rockhampton), Gladstone ‐ Mt Larcom Road, intersection upgrade; 3583253 | 0.8 | Detailed Design | IBCP-CFEP | Restricted Tender | HE2 | Jul-Sep 2025 | Up to $10m |
| Bruce Highway (Rockhampton - St Lawrence), Bolsover Street, Intersection upgrade; 854972 | 0.1 | Detailed Design | IBCP-CFEP | Restricted Tender | HE2 | Apr-Jun 2026 | Up to $10m |
| Bruce Highway (Benaraby ‐ Rockhampton), Gladstone ‐ Mt Larcom Road to Dart Creek Road, Overtaking lanes; 3589583 | 2.5 | Detailed Design | IBCP-CFEP | Restricted Tender | HE2 | Jul-Sep 2025 | Up to $10m |
| Peak Downs Highway (Clermont - Nebo), Bee Creek bridge replacement & approaches upgrade, preconstruction, 3288847 | 2.8 | Detailed Design | CFEP | Open Market | HE3, BD3, HD3, GEC3, CE3 | Oct-Dec 2025 | Up to $10m |
| Capricorn Highway (Emerald - Alpha) (Package 3), strengthen and widen pavement; 2338131 | 7 | Detailed Design | CFEP | Restricted Tender | CE1, HE1, HD1, GE1 | Apr-Jun 2026 | Up to $10m |

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

8

Design projects

| Project name | Indicative length (km) | Work type | Contract Type* | Procurement method | Prequal levels* | Approximate quarter to be called | Indicative contract value |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Western Yeppoon - Emu Park Road (Tanby Road) and Taranganba Road (Taroomball), upgrade intersection; 3057006 | 0.2 | Detailed Design | CFEP | Open Market | TBC | Jul-Sep 2025 | Up to $10m |
| Rockhampton - Emu Park Road, Hartley Street to Pattison Street, construct shared path, 3556656 | 0.8 | Design of shared paths | CFEP | Restricted Tender | HE2 | Oct-Dec 2025 | Up to $10m |
| Western Yeppoon - Emu Park Road, Vernon Street to Hill Street, construct shared path;, 3556566 | 1.5 | Design of shared paths | CFEP | Restricted Tender | HE2 | Oct-Dec 2025 | Up to $10m |

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

9

Mackay-Bucasia Road and Golf Links Road intersection, upgrade intersection

| Project description | Deliver government commitment to upgrade Mackay-Bucasia Road and Golf Links Road intersection |
| --- | --- |
| Procurement method | Restricted Tender |
| Prequal levels* | HE3, ITS2, TE2 |
| Approximate quarter to be called | Jul-Sep 2025 |

Mackay-Bucasia Road

Golf Links Road intersection

Mackay-Bucasia Road and Golf Links Road intersection indicative locality map

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

10

Maintenance

| Project name | Indicative length (km) | Work type | Contract Type* | Procurement method | Prequal levels* | Approximate quarter to be called | Indicative contract value |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2729226 - Bruce Highway 2024-25 to 2026-27 Reseal program NN & 2736321 - Bruce Highway 2024-25 to 2026-27 Reseal program state funded NN | 22.2 (in sections) | Surfacing Treatment | MIC-CO | Open Market | F1 | Jul-Sep 2025 | Up to $10m |
| 2735674 - 2024-25 to 2026-27 Skid resistance program SN | 55.8 (in sections) | Skid resistant treatment | MIC-CO | Open Market | F1 | Jan-Mar 2026 | Up to $10m |
| 2735904 - MACD D001; 2024-25 to 2026-27 Reseal program SN | 234 (in sections) | Surfacing Treatment | MIC-CO | Open Market | F1 | Jan-Mar 2026 | Up to $10m |
| CTWD D001; 2025-26 Resurfacing program; 3477856 | 275.6 (in sections) | Bitumen Reseal | MIC-CO | Open Market | F1 | Jul-Sep 2025 | Up to $10m |
| CTWD D002; Landsborough Highway (Tambo - Kynuna), resurfacing program; 3478147 | 52.8 (in sections) | Bitumen Reseal | MIC-CO | Open Market | F1 | Jul-Sep 2025 | Up to $10m |
| 2025-26 to 2026-27 Programmed Maintenance NN (3321693) | 2.6 (in sections) | Asphalt Resurfacing | MIC-CO | Open Market | A3 | Apr-Jun 2026 | Up to $10m |
| 2025-26 to 2026-27 Programmed Maintenance SN (3321766) | 250 (in sections) | Bitumen Reseals | MIC-CO | Open Market | A3 | Jul-Sep 2025 | $10m - $25m |
| FTZD D001; 2025‐26 to 2026‐27 E18 rehabilitate pavement SN; 3500082 | 26.7 (in sections) | Pavement Rehabilitation | TIC-CO | Open Market | R3 | Jul-Sep 2025 | Up to $10m |
| FTZD D001; 2025-26 to 2026-27 E29 Skid resistance management SN; 3321886 | 35 (in sections) | Water Blasting | MIC-CO | Restricted Tender | R3 | Apr-Jun 2026 | Up to $10m |

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

11

Planning projects

| Project name | Indicative length (km) | Work type | Procurement method | Pre-qual levels* | Approximate quarter to be called | Indicative contract value |
| --- | --- | --- | --- | --- | --- | --- |
| Bruce Highway (St Lawrence - Mackay), upgrade safety, planning; 3125630 | 1.3 | Options Analysis | Restricted Tender | TP2 | Oct-Dec 2025 | Up to $10m |
| Capricorn Highway (Emerald - Alpha), Anakie Railway Overpass and Medway Creek, upgrade overpass bridge, planning; 3124657 | 0.1 | Planning | Restricted Tender | ES1, CE1, GE1, HE1, HD2 | Jan-Mar 2026 | Up to $10m |
| Capricorn Highway (Duaringa - Emerald), 66.35 - 149.1km, creek crossing upgrades; 2690638 | 1.5 | Planning | Restricted Tender | HD2 | Jan-Mar 2026 | Up to $10m |
| Leichhardt Highway (Westwood - Taroom), improve road safety, planning; 3146878 | 26.8 | Planning | Restricted Tender | TE1, HE1 | Jan-Mar 2026 | Up to $10m |
| Baralaba - Woorabinda Road, upgrade Dawson Anabranch Floodway, planning; 3146747 | 0.5 | Planning | Restricted Tender | HD2 | Jan-Mar 2026 | Up to $10m |

Department of Transport and Main Roads	*See Endnotes for Contract Type, Procurement and Prequalification terms

12

Material demand

| Materials | Jul-Sep 2025 | Oct-Dec 2025 | Jan-Mar 2026 | Apr-Jun 2026 | Total |
| --- | --- | --- | --- | --- | --- |
| Asphalt - Estimated demand (tonnes) | 0 | 0 | 378 | 16,000 | 16,378 |
| Bitumen - Estimated demand (litres) | 0 | 2,710,945 | 1,889,872 | 1,267,587 | 5,868,404 |
| Granular - Estimated demand (m3) | 0 | 15,334 | 20,989 | 9,565 | 45,888 |
| Concrete - Estimated demand (m3) | 340 | 225 | 3,302 | 8,925 | 12,792 |
| Culvert - Estimated demand (linear metres) | 75 | 790 | 1,292 | 902 | 3,059 |
| Deck Units - Estimated demand | 0 | 80 | 110 | 227 | 417 |

Department of Transport and Main Roads

Contract Type, Procurement and Prequalification terms

| A | Asphalt |
| --- | --- |
| B | Bridgeworks |
| BD | Bridge Design |
| CE | Cost Estimating |
| CFEP | Consultants for Engineering Projects |
| CPA | Collaborative Project Agreement |
| DAI | Data Analysis & Insights |
| ECI | Early Contractor Involvement |
| EE | Electrical Engineering |
| ENV | Environmental Services |
| EOI | Expression of Interest |
| ES | Economic Studies |
| ETI | Early Tender Involvement |
| F | Financial Level |
| FC | Financial / Commercial |
| FREW | First Response Emergency Works |
| GE | Geotechnical Engineering |
| HD | Hydraulic Design |
| HE | Highway Engineering |
| IBCP | Infrastructure Building and Construction Panel |
| ITS | Intelligent Transport Systems |
| MIC-CO | Minor Infrastructure Contract – Construct Only |
| MIC-DC | Minor Infrastructure Contract – Design and Construct |
| MIC-SI | Minor Infrastructure Contract – Sole Invitation |

| PAF | Project Assessment Framework |
| --- | --- |
| PD | Pavement Design |
| PM | Project Management |
| PPP | Public-Private Partnership |
| QBS | Qualification Based Selection |
| R | Roadworks |
| RAMC | Road Asset Maintenance Contract |
| RM | Risk Management |
| RMPC | Road Maintenance Performance Contract |
| SE | Structural Engineering |
| SOA | Standing Offer Arrangement |
| SSMW | Small Scale Minor Works |
| TE | Traffic Engineering |
| TIC-CO | Transport Infrastructure Contract – Construct Only |
| TIC-DC | Transport Infrastructure Contract – Design and Construct |
| TIC-SI | Transport Infrastructure Contract – Sole Invitation |
| TLUM | Transport & Land Use Modelling |
| TP | Transport Planning |
| VBS | Value Based Selection |

13

Endnotes

Department of Transport and Main Roads

14

Contact

## For further information about our program email:

CQ_Program@tmr.qld.gov.au

Department of Transport and Main Roads

Thank you and stay connected

## www.tm r.q ld .g o v.au

TMRQld	@TMRQld	TMRQld	Department of Transport and Main Roads